SECURECHAT

Phase 1: Complete Sprint Planning

Detailed User Stories, Tasks & Acceptance Criteria

16 Weeks | 8 Sprints | 40+ User Stories | 778 Hours

Version 1.0 | January 2025

# Table of Contents

# Phase 1 Overview

Phase 1 delivers a complete web-based secure messaging application with hybrid post-quantum encryption, establishing the foundation for cross-platform expansion.

## Sprint Summary

| Sprint | Weeks | Focus | Points | Hours |
| --- | --- | --- | --- | --- |
| 1 | 1-2 | Foundation & Project Setup | 26 | 62 |
| 2 | 3-4 | Classical Cryptography | 37 | 95 |
| 3 | 5-6 | Post-Quantum Cryptography | 37 | 96 |
| 4 | 7-8 | Hybrid X3DH Protocol | 34 | 98 |
| 5 | 9-10 | Double Ratchet Algorithm | 34 | 105 |
| 6 | 11-12 | Backend Infrastructure | 34 | 102 |
| 7 | 13-14 | Web Client Application | 34 | 108 |
| 8 | 15-16 | Integration & Polish | 34 | 112 |

Total: 270 Story Points | 778 Estimated Hours

# Sprint 1: Foundation & Project Setup (Weeks 1-2)

Sprint Goal Establish project infrastructure, development environment, CI/CD pipeline, and Clean Architecture solution structure.

## Sprint Objectives

- Create GitHub repository with branch protection and CI/CD

- Set up containerized development environment with Docker

- Establish Clean Architecture project structure

- Configure coding standards and contribution guidelines

## Sprint Metrics

| Metric | Value |
| --- | --- |
| Story Points | 26 |
| Hours | 62 |
| Risk | Low |
| User Stories | 4 |

## User Stories

User Story US-1.1: GitHub Repository Setup As a developer, I want to have a well-organized repository structure so that I can navigate and contribute to the codebase efficiently.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 5 | 12 |

### Tasks Breakdown

Task 1: Create GitHub Repository Hours: 2 ¦ Priority: Critical Description: Initialize SecureChat repository with proper settings, branch protection, and documentation. Subtasks: - Create repo under organization - Configure settings (disable wiki, enable issues) - Add description and topics - Set up repository secrets Technical Details: Use GitHub CLI: gh repo create SecureChat --public. Enable Dependabot and security alerts. Deliverables: - GitHub repository URL - Branch protection rules configured

Task 2: Configure Branch Protection Hours: 1 ¦ Priority: High Description: Set up rules to enforce code review and status checks before merging. Subtasks: - Require PR reviews (min 1) - Require status checks - Prevent force pushes Technical Details: Apply to main and develop branches. Feature branches: feature/US-X.X-description. Deliverables: - Branch protection documentation

Task 3: Create Solution Directory Structure Hours: 3 ¦ Priority: Critical Description: Establish complete directory structure following Clean Architecture principles. Subtasks: - Create /src for source projects - Create /tests for test projects - Create /docs for documentation - Create /.github for workflows Technical Details: Structure: /src/SecureChat.{Core,Crypto,Infrastructure,Api,Web.Client} Deliverables: - Complete directory structure - Architecture diagram

Task 4: Configure EditorConfig Hours: 2 ¦ Priority: High Description: Set up code style rules for consistent formatting across developers. Subtasks: - Create .editorconfig with C# conventions - Configure naming rules - Set up analyzer settings Technical Details: Follow Microsoft C# conventions. Enable nullable reference types. Deliverables: - .editorconfig file - Code style documentation

Task 5: Create Documentation Hours: 4 ¦ Priority: Medium Description: Write README, CONTRIBUTING, CODE_OF_CONDUCT, and SECURITY documents. Subtasks: - Write README with setup instructions - Create CONTRIBUTING guide - Add CODE_OF_CONDUCT - Create issue/PR templates Technical Details: Use GitHub-flavored Markdown. Include shields.io badges. Deliverables: - README.md - CONTRIBUTING.md - CODE_OF_CONDUCT.md - SECURITY.md

### Acceptance Criteria

- ✓ Repository accessible and configured

- ✓ Branch protection prevents direct pushes

- ✓ All documentation complete

- ✓ EditorConfig enforces style

### Technical Notes

- Use signed commits

- Branch naming: feature/US-X.X-description

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Permission misconfiguration | Low | Review GitHub security docs |

User Story US-1.2: CI/CD Pipeline Setup As a developer, I want to have automated build, test, and security pipelines so that code quality is maintained automatically.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 18 |

### Tasks Breakdown

Task 1: Create Build Workflow Hours: 4 ¦ Priority: Critical Description: Set up GitHub Actions for building .NET solution on every push and PR. Subtasks: - Create .github/workflows/build.yml - Configure .NET 10 SDK - Add restore and build steps - Configure artifact upload Technical Details: Use ubuntu-latest runner. Cache NuGet packages. Build in Release mode. Deliverables: - build.yml workflow - Build status badge

Task 2: Configure Test Execution Hours: 4 ¦ Priority: Critical Description: Add automated test execution with reporting. Subtasks: - Add dotnet test step - Configure test result publishing - Set up failure notifications Technical Details: Use --logger trx. Publish with dorny/test-reporter. Deliverables: - Test execution in CI - Test results in PRs

Task 3: Set Up Code Coverage Hours: 3 ¦ Priority: High Description: Implement coverage collection with minimum 80% threshold. Subtasks: - Add coverlet.collector - Upload to Codecov - Add coverage badge - Set threshold enforcement Technical Details: Output format: cobertura. Fail if coverage drops below 80%. Deliverables: - Coverage configuration - Codecov integration

Task 4: Configure CodeQL Scanning Hours: 3 ¦ Priority: High Description: Set up security analysis for vulnerability detection. Subtasks: - Create codeql.yml workflow - Configure C# analysis - Set up weekly scans Technical Details: Use github/codeql-action. Alert on high severity. Deliverables: - Security scanning workflow

Task 5: Set Up Dependabot Hours: 2 ¦ Priority: Medium Description: Configure automatic dependency updates. Subtasks: - Create dependabot.yml - Configure update schedule - Set up auto-merge for patches Technical Details: Weekly updates, daily for security fixes. Deliverables: - Dependabot configuration

### Acceptance Criteria

- ✓ Build runs on every PR

- ✓ Tests execute with results in PR

- ✓ Coverage reports to Codecov

- ✓ Security scans running

### Technical Notes

- Cache NuGet packages

- Use concurrency groups

### Dependencies

- US-1.1

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Flaky tests | Medium | Implement retry logic |

User Story US-1.3: Development Environment As a developer, I want to have a containerized development environment so that setup is consistent and new contributors can start quickly.

| Priority | Story Points | Hours |
| --- | --- | --- |
| High | 5 | 10 |

### Tasks Breakdown

Task 1: Create Docker Compose Hours: 4 ¦ Priority: Critical Description: Create Docker Compose for local development with all services. Subtasks: - Create docker-compose.yml - Configure API service - Configure PostgreSQL - Set up volumes Technical Details: Docker Compose v3.8. PostgreSQL 16, hot reload for API. Deliverables: - docker-compose.yml - Environment documentation

Task 2: Configure PostgreSQL Hours: 2 ¦ Priority: High Description: Set up PostgreSQL container with initialization. Subtasks: - Configure image/version - Create init script - Add health check Technical Details: Image: postgres:16-alpine. Health: pg_isready. Deliverables: - PostgreSQL configuration - Init SQL script

Task 3: Create Dev Certificates Hours: 2 ¦ Priority: Medium Description: Generate SSL certificates for local HTTPS. Subtasks: - Generate dev certificates - Configure trust - Document installation Technical Details: Use dotnet dev-certs. Consider mkcert for cross-platform. Deliverables: - Development certificates - Installation guide

Task 4: Document Setup Process Hours: 2 ¦ Priority: Medium Description: Create comprehensive setup documentation. Subtasks: - Document prerequisites - Write step-by-step guide - Create troubleshooting FAQ Technical Details: Include Windows, macOS, Linux instructions. Deliverables: - DEVELOPMENT.md guide

### Acceptance Criteria

- ✓ docker-compose up starts all services

- ✓ New developer productive in 15 minutes

- ✓ Hot reload works

### Technical Notes

- Use .env for configuration

- docker-compose.override.yml for local settings

### Dependencies

- US-1.1

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Docker performance on Windows | Medium | Document WSL2 setup |

User Story US-1.4: Clean Architecture Structure As a architect, I want to have a well-organized solution following Clean Architecture so that the codebase is maintainable and testable.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 22 |

### Tasks Breakdown

Task 1: Create SecureChat.Core Hours: 3 ¦ Priority: Critical Description: Create core domain library with entities and interfaces. Subtasks: - Create class library - Add Entities folder - Add Interfaces folder - Add Exceptions folder Technical Details: Zero external dependencies. Use nullable reference types. Deliverables: - SecureChat.Core.csproj - Base interfaces

Task 2: Create SecureChat.Crypto Hours: 3 ¦ Priority: Critical Description: Create cryptographic library for all encryption operations. Subtasks: - Create class library - Add Primitives folder - Add Protocols folder - Configure NuGet packages Technical Details: Depends on Core only. Use Sodium.Core and BouncyCastle. Deliverables: - SecureChat.Crypto.csproj

Task 3: Create SecureChat.Infrastructure Hours: 3 ¦ Priority: High Description: Create infrastructure library for data access and services. Subtasks: - Create class library - Add Persistence folder - Configure EF Core Technical Details: Implements Core interfaces. Uses Npgsql. Deliverables: - SecureChat.Infrastructure.csproj

Task 4: Create SecureChat.Api Hours: 3 ¦ Priority: High Description: Create ASP.NET Core Web API project. Subtasks: - Create Web API project - Configure Minimal APIs - Set up Swagger - Add SignalR placeholder Technical Details: Use Minimal APIs. Configure Scalar for docs. Deliverables: - SecureChat.Api.csproj - Swagger UI

Task 5: Create SecureChat.Web.Client Hours: 3 ¦ Priority: High Description: Create Blazor WebAssembly client project. Subtasks: - Create Blazor WASM project - Configure AOT - Set up folders - Configure HTTP client Technical Details: Standalone WASM. Enable trimming and AOT. Deliverables: - SecureChat.Web.Client.csproj

Task 6: Create Test Projects Hours: 4 ¦ Priority: High Description: Create test projects for each source project. Subtasks: - Create 5 test projects - Configure xUnit - Add Moq and FluentAssertions Technical Details: Use xUnit. Add coverlet.collector. Deliverables: - Test projects configured

Task 7: Configure Dependencies Hours: 3 ¦ Priority: High Description: Set up project references following Clean Architecture. Subtasks: - Verify Core has no references - Configure dependency flow - Add architectural tests Technical Details: Use ArchUnitNET to enforce rules. Deliverables: - Correct references - Architectural tests

### Acceptance Criteria

- ✓ Solution builds successfully

- ✓ References follow Clean Architecture

- ✓ Tests discoverable

- ✓ Swagger accessible

### Technical Notes

- Use Directory.Build.props for shared settings

- Enable ImplicitUsings

### Dependencies

- US-1.1

- US-1.3

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Circular dependencies | High | Architectural tests from day one |

# Sprint 2: Classical Cryptography (Weeks 3-4)

Sprint Goal Implement all classical cryptographic primitives: Ed25519, X25519, AES-256-GCM, and HKDF with comprehensive testing.

## Sprint Objectives

- Implement Ed25519 key generation and digital signatures

- Implement X25519 Diffie-Hellman key exchange

- Implement AES-256-GCM authenticated encryption

- Implement HKDF-SHA256 key derivation

- Achieve >90% test coverage with standard test vectors

## Sprint Metrics

| Metric | Value |
| --- | --- |
| Story Points | 37 |
| Hours | 95 |
| Risk | Medium |
| User Stories | 5 |

## User Stories

User Story US-2.1: Key Pair Generation As a system, I want to generate secure Ed25519 and X25519 key pairs so that users can establish cryptographic identity and perform key exchanges.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 24 |

### Tasks Breakdown

Task 1: Implement Ed25519 Key Generation Hours: 4 ¦ Priority: Critical Description: Create Ed25519 key pairs for digital signatures using libsodium. Subtasks: - Create Ed25519KeyPair class - Implement Generate() method - Add key validation - Implement IDisposable - Add fingerprint generation Technical Details: Use Sodium.Core. Ed25519 private key is 64 bytes. Implement secure memory handling. Deliverables: - Ed25519KeyPair.cs - Unit tests with RFC 8032 vectors

Task 2: Implement X25519 Key Generation Hours: 4 ¦ Priority: Critical Description: Create X25519 key pairs for Diffie-Hellman key exchange. Subtasks: - Create X25519KeyPair class - Implement Generate() method - Add key validation - Implement FromPrivateKey() Technical Details: X25519 keys are 32 bytes each. Clamp per RFC 7748. Deliverables: - X25519KeyPair.cs - RFC 7748 tests

Task 3: Create Key Interfaces Hours: 3 ¦ Priority: High Description: Define interfaces for key pairs to enable abstraction. Subtasks: - Create IKeyPair interface - Create ISigningKeyPair - Create IKeyExchangeKeyPair - Add KeyPairType enum Technical Details: Interfaces in Core, implementations in Crypto. Deliverables: - Interface files - Documentation

Task 4: Implement Key Serialization Hours: 4 ¦ Priority: High Description: Implement secure serialization for key storage and transmission. Subtasks: - Create KeySerializer class - Implement public key serialization - Implement encrypted private key serialization - Add versioning Technical Details: Use MessagePack. Encrypt private keys with AES-256-GCM. Deliverables: - KeySerializer.cs - Format specification

Task 5: Add Key Validation Hours: 3 ¦ Priority: Medium Description: Implement validation to detect corrupted or malicious keys. Subtasks: - Create KeyValidator class - Check Ed25519 on-curve - Check X25519 non-zero - Add small subgroup check Technical Details: Constant-time comparison. Check against known bad keys. Deliverables: - KeyValidator.cs - Security tests

Task 6: Write Comprehensive Tests Hours: 6 ¦ Priority: Critical Description: Create thorough tests with standard test vectors. Subtasks: - Add RFC 8032 Ed25519 vectors - Add RFC 7748 X25519 vectors - Test serialization - Add benchmarks Technical Details: Use xUnit [Theory]. Minimum 20 test cases per algorithm. Deliverables: - Test files - Benchmark results

### Acceptance Criteria

- ✓ Key generation <10ms

- ✓ All RFC vectors pass

- ✓ Serialization round-trips

- ✓ Invalid keys rejected

### Technical Notes

- libsodium ops are constant-time

- Never log private keys

### Dependencies

- US-1.4

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Native library loading | High | Test all platforms |

User Story US-2.2: Digital Signatures As a system, I want to create and verify Ed25519 digital signatures so that message authenticity can be cryptographically verified.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 18 |

### Tasks Breakdown

Task 1: Implement Ed25519 Signing Hours: 4 ¦ Priority: Critical Description: Create signatures with proper message handling. Subtasks: - Create Ed25519Signer class - Implement Sign() method - Add detached signature mode - Create Signature class Technical Details: Signatures are 64 bytes. Use SignDetached(). Deliverables: - Ed25519Signer.cs - ISigner interface

Task 2: Implement Ed25519 Verification Hours: 4 ¦ Priority: Critical Description: Verify signatures with malleability protection. Subtasks: - Create Ed25519Verifier class - Implement Verify() method - Add batch verification - Check non-canonical S values Technical Details: Use VerifyDetached(). Reject non-canonical signatures. Deliverables: - Ed25519Verifier.cs - IVerifier interface

Task 3: Create Signature Abstraction Hours: 2 ¦ Priority: High Description: Define interface for algorithm flexibility. Subtasks: - Create IDigitalSignatureAlgorithm - Add SignatureAlgorithm enum - Document selection guidelines Technical Details: Support async operations with CancellationToken. Deliverables: - Interface file - Documentation

Task 4: Implement Signature Serialization Hours: 2 ¦ Priority: Medium Description: Create serialization format with algorithm identification. Subtasks: - Create Signature class - Implement ToBytes/FromBytes - Add versioning Technical Details: Format: version ¦ algorithm ¦ signature data. Deliverables: - Serialization methods - Format spec

Task 5: Write RFC 8032 Tests Hours: 4 ¦ Priority: Critical Description: Test with official test vectors. Subtasks: - Implement all RFC 8032 vectors - Test empty message - Test corrupted signatures - Add malleability tests Technical Details: Include TEST1, TEST2, TEST3, TEST1024 vectors. Deliverables: - Test files - Vector data

Task 6: Benchmark Performance Hours: 2 ¦ Priority: Medium Description: Measure signing and verification performance. Subtasks: - Benchmark small/medium/large messages - Compare batch verification Technical Details: Target: sign <1ms, verify <1ms for small messages. Deliverables: - Benchmark results

### Acceptance Criteria

- ✓ All RFC 8032 vectors pass

- ✓ Sign/verify <5ms for 1KB

- ✓ Non-canonical rejected

- ✓ Batch verification works

### Technical Notes

- Ed25519 is deterministic

- Consider Ed25519ctx for domain separation

### Dependencies

- US-2.1

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Signature malleability | High | Strict S value checking |

User Story US-2.3: X25519 Key Exchange As a system, I want to perform secure Diffie-Hellman key exchange so that shared secrets can be established over insecure channels.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 18 |

### Tasks Breakdown

Task 1: Implement X25519 DH Hours: 4 ¦ Priority: Critical Description: Implement core X25519 scalar multiplication. Subtasks: - Create X25519 static class - Implement ComputeSharedSecret() - Add all-zeros check - Ensure constant-time Technical Details: Use Sodium.ScalarMult. Never use raw secret directly. Deliverables: - X25519.cs - Security documentation

Task 2: Create Shared Secret Derivation Hours: 3 ¦ Priority: Critical Description: Implement proper derivation combining DH with KDF. Subtasks: - Create DiffieHellmanResult class - Implement DeriveKey() - Add salt support - Document patterns Technical Details: Always use HKDF on raw DH output. Deliverables: - DiffieHellmanResult.cs - Usage docs

Task 3: Implement Constant-Time Comparison Hours: 3 ¦ Priority: Critical Description: Prevent timing attacks in secret comparison. Subtasks: - Create CryptoCompare class - Implement ConstantTimeEquals() - Verify timing behavior Technical Details: Use XOR accumulator pattern. Deliverables: - CryptoCompare.cs - Timing tests

Task 4: Add DH Validation Hours: 2 ¦ Priority: High Description: Validate DH results to detect malicious inputs. Subtasks: - Check all-zeros result - Validate public key points - Check known bad keys Technical Details: Reject low-order points and small subgroup attacks. Deliverables: - Validation logic - Bad key constants

Task 5: Write RFC 7748 Tests Hours: 4 ¦ Priority: Critical Description: Test with official vectors. Subtasks: - Implement RFC 7748 Section 5.2 vectors - Add iterated test (1M iterations) - Test bad keys Technical Details: Iteration test validates long-term correctness. Deliverables: - Test file - Vector data

Task 6: Document Security Hours: 2 ¦ Priority: Medium Description: Create comprehensive security documentation. Subtasks: - Document key requirements - Explain timing prevention - Provide examples Technical Details: Accessible to non-crypto developers. Deliverables: - X25519_SECURITY.md

### Acceptance Criteria

- ✓ All RFC 7748 vectors pass

- ✓ DH <2ms

- ✓ All-zeros rejected

- ✓ Constant-time verified

### Technical Notes

- X25519 is Montgomery curve

- Contributing factors prevent invalid curve attacks

### Dependencies

- US-2.1

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Invalid curve attack | Critical | Validate all public keys |

User Story US-2.4: AES-256-GCM Encryption As a system, I want to encrypt messages with authenticated encryption so that confidentiality and integrity are protected simultaneously.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 22 |

### Tasks Breakdown

Task 1: Implement AES-GCM Encryption Hours: 4 ¦ Priority: Critical Description: Implement encryption with proper nonce and AAD handling. Subtasks: - Create Aes256Gcm class - Implement Encrypt() - Validate key/nonce lengths - Generate auth tag Technical Details: Nonce: 12 bytes, Tag: 16 bytes. Max message: 2^36-32 bytes. Deliverables: - Aes256Gcm.cs - IAuthenticatedEncryption interface

Task 2: Implement AES-GCM Decryption Hours: 4 ¦ Priority: Critical Description: Implement decryption with tag verification. Subtasks: - Implement Decrypt() - Verify auth tag first - Clear on failure - Throw CryptoException Technical Details: No plaintext leakage on failure. Constant-time tag comparison. Deliverables: - Decryption methods - CryptoException class

Task 3: Create Nonce Generation Hours: 3 ¦ Priority: Critical Description: Implement secure, unique nonce generation. Subtasks: - Create NonceGenerator class - Implement random nonce mode - Add counter mode option - Document requirements Technical Details: Random: collision after 2^48 messages. Consider hybrid approach. Deliverables: - NonceGenerator.cs - Nonce management docs

Task 4: Implement AAD Support Hours: 3 ¦ Priority: High Description: Support additional authenticated data. Subtasks: - Add AAD parameter - Handle empty AAD - Document usage patterns Technical Details: AAD authenticated but not encrypted. Use for headers. Deliverables: - AAD implementation - Usage documentation

Task 5: Add Size Validation Hours: 2 ¦ Priority: Medium Description: Validate message sizes to prevent overflow. Subtasks: - Define max size constant - Add size checks - Document limits Technical Details: Practical limit: 64MB in-memory. Chunk larger messages. Deliverables: - Size validation - Limit documentation

Task 6: Write NIST Tests Hours: 4 ¦ Priority: Critical Description: Test with NIST AES-GCM vectors. Subtasks: - Parse NIST CAVP vectors - Test encrypt/decrypt - Test auth failure detection Technical Details: Include all key sizes and failure cases. Deliverables: - Test file - NIST vector data

Task 7: Benchmark Throughput Hours: 2 ¦ Priority: Low Description: Measure encryption performance. Subtasks: - Benchmark various sizes - Measure throughput MB/s - Check hardware acceleration Technical Details: Expected: >1GB/s with AES-NI. Deliverables: - Benchmark results

### Acceptance Criteria

- ✓ All NIST vectors pass

- ✓ >100MB/s throughput

- ✓ Nonce reuse prevented

- ✓ Auth failures throw

### Technical Notes

- GCM is stream cipher - never reuse nonce

- Consider AES-GCM-SIV for nonce misuse resistance

### Dependencies

- US-2.1

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Nonce reuse | Critical | Counter mode or collision detection |

User Story US-2.5: HKDF Key Derivation As a system, I want to derive cryptographic keys from shared secrets so that secure uniform keys can be generated for various operations.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 5 | 13 |

### Tasks Breakdown

Task 1: Implement HKDF Extract Hours: 3 ¦ Priority: Critical Description: Create pseudorandom key from input keying material. Subtasks: - Create Hkdf class - Implement Extract() - Handle null salt - Validate IKM Technical Details: Extract: PRK = HMAC-SHA256(salt, IKM). Output: 32 bytes. Deliverables: - Hkdf.cs - Extract tests

Task 2: Implement HKDF Expand Hours: 3 ¦ Priority: Critical Description: Produce output keying material of desired length. Subtasks: - Implement Expand() - Support up to 8160 bytes output - Clear intermediates Technical Details: Expand: T(i) = HMAC(PRK, T(i-1) ¦ info ¦ i). Deliverables: - Expand implementation - Tests

Task 3: Create Convenience Method Hours: 2 ¦ Priority: High Description: Combine Extract and Expand in single call. Subtasks: - Implement DeriveKey() - Add length constants - Clear PRK after use Technical Details: Most common usage pattern. Deliverables: - DeriveKey method - Constants

Task 4: Add Info Parameter Support Hours: 2 ¦ Priority: Medium Description: Implement domain separation via info parameter. Subtasks: - Support byte/string info - Document best practices - Provide standard strings Technical Details: Format: 'SecureChat v1 <purpose>'. Deliverables: - Info handling - Standard strings

Task 5: Write RFC 5869 Tests Hours: 3 ¦ Priority: Critical Description: Test with official vectors. Subtasks: - Implement all RFC 5869 test cases - Add edge cases - Cross-verify Technical Details: Appendix A provides test vectors. Deliverables: - Test file - Vector data

### Acceptance Criteria

- ✓ All RFC 5869 vectors pass

- ✓ Consistent derivation

- ✓ Proper cleanup

### Technical Notes

- Salt provides entropy, info provides separation

- Never derive multiple keys without differentiated info

### Dependencies

- US-2.3

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Info collision | High | Centralized info management |

# Sprint 3: Post-Quantum Cryptography (Weeks 5-6)

Sprint Goal Integrate CRYSTALS-Kyber and CRYSTALS-Dilithium algorithms, create hybrid key structures.

## Sprint Objectives

- Implement Kyber-768 KEM

- Implement Dilithium-3 signatures

- Create hybrid key pairs

- Implement hybrid shared secret derivation

## Sprint Metrics

| Metric | Value |
| --- | --- |
| Story Points | 37 |
| Hours | 96 |
| Risk | High |
| User Stories | 4 |

## User Stories

User Story US-3.1: Kyber Key Encapsulation As a system, I want to perform quantum-resistant key encapsulation so that shared secrets are protected against quantum attacks.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 13 | 30 |

### Tasks Breakdown

Task 1: Integrate BouncyCastle Hours: 4 ¦ Priority: Critical Description: Add BouncyCastle package and configure Kyber. Subtasks: - Add NuGet package - Verify Kyber-768 - Create wrapper structure Technical Details: Use BouncyCastle.Cryptography v2.3+. Deliverables: - Package integration

Task 2: Create KEM Interface Hours: 3 ¦ Priority: High Description: Define key encapsulation interface. Subtasks: - Create IKeyEncapsulationMechanism - Define Encapsulate/Decapsulate - Add KemAlgorithm enum Technical Details: Generic enough for future algorithms. Deliverables: - Interface file

Task 3: Implement Key Generation Hours: 4 ¦ Priority: Critical Description: Generate Kyber-768 key pairs. Subtasks: - Create KyberKeyPair class - Configure parameters - Validate sizes (pub: 1184, priv: 2400) Technical Details: Use KyberKeyPairGenerator. Deliverables: - KyberKeyPair.cs

Task 4: Implement Encapsulation Hours: 4 ¦ Priority: Critical Description: Create ciphertext and shared secret. Subtasks: - Create KyberKem class - Implement Encapsulate() - Validate public key Technical Details: Ciphertext: 1088 bytes, secret: 32 bytes. Deliverables: - KyberKem.cs

Task 5: Implement Decapsulation Hours: 4 ¦ Priority: Critical Description: Recover shared secret from ciphertext. Subtasks: - Implement Decapsulate() - Handle implicit rejection - Validate ciphertext Technical Details: Implicit rejection prevents CCA attacks. Deliverables: - Decapsulation method

Task 6: Key Serialization Hours: 3 ¦ Priority: High Description: Serialize Kyber keys. Subtasks: - Implement serialization - Add version prefix Technical Details: Support encrypted private keys. Deliverables: - Serialization methods

Task 7: KAT Vector Tests Hours: 6 ¦ Priority: Critical Description: Test with NIST KAT vectors. Subtasks: - Parse KAT files - Test all operations - Add negative tests Technical Details: NIST provides official vectors. Deliverables: - Test files

Task 8: Performance Benchmarks Hours: 2 ¦ Priority: Medium Description: Benchmark Kyber operations. Subtasks: - Benchmark keygen/encaps/decaps Technical Details: Expected: keygen ~50ms, encaps/decaps ~20ms. Deliverables: - Benchmark results

### Acceptance Criteria

- ✓ All KAT vectors pass

- ✓ Keygen <100ms

- ✓ Encaps/decaps <50ms

### Technical Notes

- Kyber-768 = 128-bit PQ security

### Dependencies

- US-2.1

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Performance insufficient | Medium | Benchmark early |

User Story US-3.2: Dilithium Signatures As a system, I want to create quantum-resistant digital signatures so that identity keys remain secure against quantum attacks.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 21 |

### Tasks Breakdown

Task 1: Implement Key Generation Hours: 4 ¦ Priority: Critical Description: Generate Dilithium-3 key pairs. Subtasks: - Create DilithiumKeyPair class - Configure parameters - Validate sizes (pub: 1952, priv: 4016) Technical Details: NIST Level 3 security. Deliverables: - DilithiumKeyPair.cs

Task 2: Implement Signing Hours: 4 ¦ Priority: Critical Description: Create Dilithium signatures. Subtasks: - Create DilithiumSigner class - Implement Sign() - Clear private key after Technical Details: Signatures: 3293 bytes. Non-deterministic. Deliverables: - DilithiumSigner.cs

Task 3: Implement Verification Hours: 4 ¦ Priority: Critical Description: Verify Dilithium signatures. Subtasks: - Create DilithiumVerifier class - Implement Verify() - Return boolean Technical Details: Verification faster than signing. Deliverables: - DilithiumVerifier.cs

Task 4: Serialization Hours: 2 ¦ Priority: High Description: Serialize signatures. Subtasks: - Create format with algorithm ID Technical Details: Compatible with hybrid signatures. Deliverables: - Serialization

Task 5: KAT Tests Hours: 5 ¦ Priority: Critical Description: Test with NIST vectors. Subtasks: - Parse vectors - Test all operations Technical Details: Verify byte-for-byte match. Deliverables: - Test files

Task 6: Benchmarks Hours: 2 ¦ Priority: Medium Description: Compare with Ed25519. Subtasks: - Benchmark all operations Technical Details: 10-50x slower than Ed25519. Deliverables: - Comparison table

### Acceptance Criteria

- ✓ All KAT vectors pass

- ✓ Sign <50ms

- ✓ Verify <30ms

### Technical Notes

- Only for identity, not per-message

### Dependencies

- US-3.1

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Large signature size | Low | Only for identity |

User Story US-3.3: Hybrid Key Pairs As a system, I want to create combined classical and PQ key pairs so that protection against both classical and quantum attacks.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 22 |

### Tasks Breakdown

Task 1: Design Data Structure Hours: 3 ¦ Priority: Critical Description: Design hybrid key pair structure. Subtasks: - Define HybridIdentityKeyPair - Define HybridKeyExchangeKeyPair Technical Details: Public = classical ¦¦ PQ. Deliverables: - Design document

Task 2: Implement Identity Key Pair Hours: 4 ¦ Priority: Critical Description: Ed25519 + Dilithium hybrid. Subtasks: - Create class - Implement hybrid signing - Implement verification Technical Details: Total signature: 64 + 3293 = 3357 bytes. Deliverables: - HybridIdentityKeyPair.cs

Task 3: Implement Exchange Key Pair Hours: 4 ¦ Priority: Critical Description: X25519 + Kyber hybrid. Subtasks: - Create class - Generate both components Technical Details: Public: 32 + 1184 = 1216 bytes. Deliverables: - HybridKeyExchangeKeyPair.cs

Task 4: Serialization Format Hours: 4 ¦ Priority: High Description: Serialize hybrid keys. Subtasks: - Define format - Implement serialize/deserialize Technical Details: Version ¦ type ¦ classical ¦ PQ. Deliverables: - Serialization

Task 5: Key Fingerprinting Hours: 3 ¦ Priority: Medium Description: Generate human-readable fingerprints. Subtasks: - Create fingerprint from combined key - Format as hex groups Technical Details: SHA-256, formatted as 'XXXX XXXX...' Deliverables: - Fingerprint generation

Task 6: Tests Hours: 4 ¦ Priority: High Description: Test hybrid functionality. Subtasks: - Test generation - Test signing requires both valid Technical Details: Verification fails if either fails. Deliverables: - Test files

### Acceptance Criteria

- ✓ Both components generated

- ✓ Verification requires both valid

- ✓ Serialization works

### Technical Notes

- Both must succeed for security

### Dependencies

- US-2.1

- US-2.2

- US-3.1

- US-3.2

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Large key sizes | Medium | Document requirements |

User Story US-3.4: Hybrid Shared Secret As a system, I want to combine classical and PQ shared secrets so that security even if one algorithm is broken.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 23 |

### Tasks Breakdown

Task 1: Design Combination Strategy Hours: 4 ¦ Priority: Critical Description: Design secure secret combination. Subtasks: - Research approaches - Choose concatenation + KDF Technical Details: final = HKDF(x25519 ¦¦ kyber, salt, info). Deliverables: - Strategy document

Task 2: Implement Combination Hours: 6 ¦ Priority: Critical Description: Combine X25519 and Kyber secrets. Subtasks: - Create HybridKeyExchange class - Implement initiator/responder - Apply HKDF Technical Details: 64 bytes input to HKDF, 32 bytes output. Deliverables: - HybridKeyExchange.cs

Task 3: Create Hybrid KDF Hours: 4 ¦ Priority: High Description: KDF wrapper for hybrid derivation. Subtasks: - Create HybridKdf class - Define standard salt/info Technical Details: Salt: 'SecureChat Hybrid KDF v1'. Deliverables: - HybridKdf.cs

Task 4: Domain Separation Hours: 3 ¦ Priority: High Description: Implement context separation. Subtasks: - Define domain strings - Create context builder Technical Details: Format: 'SecureChat¦v1¦operation¦context'. Deliverables: - Domain constants

Task 5: Security Documentation Hours: 4 ¦ Priority: High Description: Document security properties. Subtasks: - Analyze under classical/quantum attacker - Document assumptions Technical Details: IND-CCA2 if either provides it. Deliverables: - HYBRID_SECURITY.md

Task 6: Tests Hours: 4 ¦ Priority: Critical Description: Test hybrid exchange. Subtasks: - Test both parties derive same secret - Test uniqueness Technical Details: Deterministic given same inputs. Deliverables: - Test files

### Acceptance Criteria

- ✓ Both parties derive same secret

- ✓ Domain separation works

- ✓ Security documented

### Technical Notes

- Concatenation preferred over XOR

### Dependencies

- US-2.3

- US-2.5

- US-3.1

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Incorrect combination | Critical | Follow established patterns |

# Sprint 4: Hybrid X3DH Protocol (Weeks 7-8)

Sprint Goal Implement complete Hybrid Post-Quantum X3DH key agreement protocol.

## Sprint Objectives

- Implement pre-key bundle generation

- Implement X3DH initiator

- Implement X3DH responder

- Create session initialization

## Sprint Metrics

| Metric | Value |
| --- | --- |
| Story Points | 34 |
| Hours | 98 |
| Risk | High |
| User Stories | 4 |

## User Stories

User Story US-4.1: Pre-Key Bundle Generation As a user, I want to generate and publish pre-key bundles so that others can initiate conversations when I'm offline.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 24 |

### Tasks Breakdown

Task 1: Design PreKeyBundle Hours: 3 ¦ Priority: Critical Description: Design bundle data structure. Subtasks: - Define all fields - Include hybrid identity key - Include signed pre-key - Include one-time pre-keys Technical Details: Bundle: regId, identityKey, signedPreKey + sig, oneTimePreKeys[]. Deliverables: - PreKeyBundle.cs

Task 2: Implement Signed Pre-Key Hours: 4 ¦ Priority: Critical Description: Generate signed pre-keys. Subtasks: - Create SignedPreKey class - Sign with identity key - Add key ID and timestamp Technical Details: Rotate weekly, keep old for 30 days. Deliverables: - SignedPreKey.cs

Task 3: Implement One-Time Pre-Keys Hours: 4 ¦ Priority: Critical Description: Batch generate one-time keys. Subtasks: - Create OneTimePreKey class - Implement batch generation (100) - Track depletion Technical Details: Replenish when <20 remaining. Deliverables: - OneTimePreKey.cs

Task 4: Bundle Serialization Hours: 4 ¦ Priority: High Description: Serialize bundles for transmission. Subtasks: - Define format - Implement serialize/deserialize Technical Details: Binary with length prefixes. Deliverables: - Serialization methods

Task 5: Bundle Validation Hours: 3 ¦ Priority: High Description: Validate received bundles. Subtasks: - Validate key formats - Verify signature - Check freshness Technical Details: Reject invalid/expired bundles. Deliverables: - Validation logic

Task 6: Tests Hours: 6 ¦ Priority: Critical Description: Test bundle functionality. Subtasks: - Test generation - Test serialization - Test validation Technical Details: >90% coverage. Deliverables: - Test files

### Acceptance Criteria

- ✓ Bundles generate correctly

- ✓ Signatures verify

- ✓ One-time keys unique

- ✓ Serialization works

### Technical Notes

- Upload on registration

- Clients fetch to initiate

### Dependencies

- US-3.3

- US-3.4

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Large bundle size | Medium | Compress, lazy load |

User Story US-4.2: X3DH Initiator As a sender, I want to perform X3DH as initiator so that I can establish shared secret with recipient.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 10 | 28 |

### Tasks Breakdown

Task 1: Implement DH Calculations Hours: 6 ¦ Priority: Critical Description: Compute DH1-DH4 values. Subtasks: - DH1: IK_A, SPK_B - DH2: EK_A, IK_B - DH3: EK_A, SPK_B - DH4: EK_A, OPK_B (optional) Technical Details: Combine X25519 results. Deliverables: - DH calculation code

Task 2: Add Kyber Encapsulation Hours: 6 ¦ Priority: Critical Description: Perform Kyber KEM for each exchange. Subtasks: - Encapsulate to SPK Kyber - Encapsulate to OPK Kyber (if present) Technical Details: Produces ciphertexts for responder. Deliverables: - Kyber integration

Task 3: Combine Shared Secrets Hours: 4 ¦ Priority: Critical Description: Derive master secret from all inputs. Subtasks: - Concatenate DH outputs - Concatenate Kyber secrets - Apply HKDF Technical Details: Master = HKDF(DH1¦¦DH2¦¦DH3¦¦DH4¦¦K1¦¦K2). Deliverables: - Secret combination

Task 4: Create Initial Message Hours: 4 ¦ Priority: Critical Description: Build message with all public data. Subtasks: - Include identity key - Include ephemeral key - Include Kyber ciphertexts Technical Details: Recipient uses to derive same secret. Deliverables: - InitialMessage structure

Task 5: Handle No OPK Case Hours: 3 ¦ Priority: Medium Description: Support when no one-time key available. Subtasks: - Omit DH4 and K2 - Adjust derivation Technical Details: Less forward secrecy without OPK. Deliverables: - OPK handling

Task 6: Tests Hours: 5 ¦ Priority: Critical Description: Test initiator protocol. Subtasks: - Test with/without OPK - Verify secret matches responder Technical Details: Cross-verify both sides. Deliverables: - Test files

### Acceptance Criteria

- ✓ All DH computed correctly

- ✓ Kyber ciphertexts valid

- ✓ Secret matches responder

- ✓ Initial message complete

### Technical Notes

- Ephemeral key generated fresh

- OPK provides extra forward secrecy

### Dependencies

- US-4.1

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Protocol mismatch | High | Test vectors |

User Story US-4.3: X3DH Responder As a recipient, I want to process X3DH initial messages so that I can derive shared secret for secure communication.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 10 | 26 |

### Tasks Breakdown

Task 1: Parse Initial Message Hours: 3 ¦ Priority: Critical Description: Extract and validate message contents. Subtasks: - Parse identity key - Parse ephemeral key - Parse Kyber ciphertexts Technical Details: Validate all formats. Deliverables: - Message parsing

Task 2: Perform DH Calculations Hours: 6 ¦ Priority: Critical Description: Compute DH values (responder side). Subtasks: - DH1: SPK_B, IK_A - DH2: IK_B, EK_A - DH3: SPK_B, EK_A - DH4: OPK_B, EK_A Technical Details: Symmetric to initiator. Deliverables: - DH code

Task 3: Kyber Decapsulation Hours: 6 ¦ Priority: Critical Description: Recover Kyber shared secrets. Subtasks: - Decapsulate SPK ciphertext - Decapsulate OPK ciphertext Technical Details: Use corresponding private keys. Deliverables: - Decapsulation code

Task 4: Derive Shared Secret Hours: 4 ¦ Priority: Critical Description: Combine all inputs identically. Subtasks: - Same concatenation order - Same HKDF parameters Technical Details: Must match initiator exactly. Deliverables: - Secret derivation

Task 5: Consume One-Time Key Hours: 3 ¦ Priority: High Description: Mark OPK as used. Subtasks: - Delete OPK after use - Handle missing OPK Technical Details: OPK never reused. Deliverables: - Key consumption

Task 6: Tests Hours: 4 ¦ Priority: Critical Description: Test responder protocol. Subtasks: - Verify secret matches initiator - Test all edge cases Technical Details: End-to-end verification. Deliverables: - Test files

### Acceptance Criteria

- ✓ Same secret as initiator

- ✓ Invalid messages rejected

- ✓ OPK consumed properly

### Technical Notes

- Look up pre-keys by ID

- Handle replay attempts

### Dependencies

- US-4.1

- US-4.2

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Key lookup failure | Medium | Proper error handling |

User Story US-4.4: Session Initialization As a system, I want to initialize Double Ratchet sessions from X3DH so that message encryption can begin.

| Priority | Story Points | Hours |
| --- | --- | --- |
| High | 6 | 20 |

### Tasks Breakdown

Task 1: Design Session State Hours: 4 ¦ Priority: Critical Description: Define all session state fields. Subtasks: - Root key - Sending/receiving chains - Ratchet keys - Message counters Technical Details: Persist across restarts. Deliverables: - Session class design

Task 2: Initialize from X3DH Hours: 4 ¦ Priority: Critical Description: Create session from shared secret. Subtasks: - Derive root key - Initialize chain keys - Set initial ratchet keys Technical Details: Asymmetric for initiator/responder. Deliverables: - Initialization code

Task 3: Derive Initial Keys Hours: 4 ¦ Priority: Critical Description: Derive all initial key material. Subtasks: - Root key from master - First sending chain - First receiving chain Technical Details: Use HKDF with domain separation. Deliverables: - Key derivation

Task 4: Session Persistence Hours: 4 ¦ Priority: High Description: Store session state securely. Subtasks: - Define storage format - Encrypt sensitive state Technical Details: Encrypted at rest. Deliverables: - Persistence code

Task 5: Tests Hours: 4 ¦ Priority: Critical Description: Test session initialization. Subtasks: - Verify both sides compatible - Test persistence Technical Details: Ready for Double Ratchet. Deliverables: - Test files

### Acceptance Criteria

- ✓ Sessions initialize correctly

- ✓ Keys derived properly

- ✓ State persists

- ✓ Ready for messaging

### Technical Notes

- Initiator/responder have different initial state

### Dependencies

- US-4.2

- US-4.3

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| State corruption | High | Atomic updates |

# Sprint 5: Double Ratchet Algorithm (Weeks 9-10)

Sprint Goal Implement complete Hybrid Double Ratchet for message encryption with forward secrecy.

## Sprint Objectives

- Implement symmetric ratchet

- Implement hybrid DH ratchet

- Create message encryption/decryption

- Handle out-of-order messages

- Add session persistence

## Sprint Metrics

| Metric | Value |
| --- | --- |
| Story Points | 34 |
| Hours | 105 |
| Risk | High |
| User Stories | 5 |

## User Stories

User Story US-5.1: Symmetric Ratchet As a system, I want to perform symmetric key ratcheting so that each message has unique encryption key.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 5 | 18 |

### Tasks Breakdown

Task 1: Chain Key Derivation Hours: 4 ¦ Priority: Critical Description: Derive successive chain keys. Subtasks: - Create ChainKey class - Implement Advance() - Track index Technical Details: CK_next = HKDF(CK, constant_1). Deliverables: - ChainKey.cs

Task 2: Message Key Derivation Hours: 4 ¦ Priority: Critical Description: Derive message-specific keys. Subtasks: - Create MessageKey class - Derive enc key and IV Technical Details: MK = HKDF(CK, constant_2). Deliverables: - MessageKey.cs

Task 3: Chain State Management Hours: 4 ¦ Priority: High Description: Manage sending/receiving chains. Subtasks: - Create SendingChain - Create ReceivingChain - Track message numbers Technical Details: Handle skipped messages. Deliverables: - Chain classes

Task 4: Tests Hours: 6 ¦ Priority: Critical Description: Test ratchet correctness. Subtasks: - Test unique keys - Test proper cleanup Technical Details: Verify security properties. Deliverables: - Test files

### Acceptance Criteria

- ✓ Chain advances correctly

- ✓ Keys unique per message

- ✓ Old keys deleted

### Technical Notes

- Delete chain key after deriving message key

### Dependencies

- US-4.4

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Key reuse | Critical | Strict advancement |

User Story US-5.2: Hybrid DH Ratchet As a system, I want to perform hybrid DH ratcheting so that new shared secrets established regularly for post-compromise security.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 26 |

### Tasks Breakdown

Task 1: DH Ratchet Step Hours: 5 ¦ Priority: Critical Description: Perform X25519 ratchet. Subtasks: - Generate new key pair - Compute DH with received key Technical Details: On receiving with new ratchet key. Deliverables: - DH ratchet code

Task 2: Kyber Ratchet Step Hours: 6 ¦ Priority: Critical Description: Perform Kyber ratchet. Subtasks: - Encapsulate/decapsulate as appropriate Technical Details: KEM alongside DH. Deliverables: - Kyber ratchet code

Task 3: Combine Ratchet Outputs Hours: 4 ¦ Priority: Critical Description: Derive new root and chain keys. Subtasks: - Concatenate DH and Kyber - Update root key - Initialize new chain Technical Details: RK, CK = HKDF(RK, DH¦¦Kyber). Deliverables: - Combination code

Task 4: New Key Pair Generation Hours: 4 ¦ Priority: High Description: Generate ratchet keys on send. Subtasks: - Generate after receiving - Include in message header Technical Details: Triggers recipient ratchet. Deliverables: - Key generation

Task 5: Tests Hours: 5 ¦ Priority: Critical Description: Test DH ratchet. Subtasks: - Test both parties advance - Test key derivation Technical Details: Verify synchronization. Deliverables: - Test files

### Acceptance Criteria

- ✓ Ratchet advances on receive

- ✓ Both parties derive same keys

- ✓ Old keys deleted

### Technical Notes

- Ratchet step on first message with new key

### Dependencies

- US-5.1

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Desynchronization | High | Careful state management |

User Story US-5.3: Message Encryption As a sender, I want to encrypt messages securely so that only intended recipient can read messages.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 22 |

### Tasks Breakdown

Task 1: Encryption Wrapper Hours: 4 ¦ Priority: Critical Description: Implement message encryption. Subtasks: - Get message key from chain - Encrypt plaintext Technical Details: AES-256-GCM. Deliverables: - Encrypt method

Task 2: Header Construction Hours: 3 ¦ Priority: Critical Description: Build message header. Subtasks: - Include ratchet public key - Include message number - Include previous chain length Technical Details: Header needed for decryption. Deliverables: - Header structure

Task 3: Header Encryption Hours: 4 ¦ Priority: Medium Description: Optionally encrypt header. Subtasks: - Derive header key - Encrypt with AES-GCM Technical Details: Metadata protection. Deliverables: - Header encryption

Task 4: Padding Hours: 3 ¦ Priority: Medium Description: Hide message length. Subtasks: - Apply PKCS#7 padding - Add random extension Technical Details: Prevent length analysis. Deliverables: - Padding code

Task 5: State Updates Hours: 4 ¦ Priority: Critical Description: Update ratchet state after send. Subtasks: - Advance sending chain - Update message counter Technical Details: Atomic state update. Deliverables: - State update code

Task 6: Tests Hours: 4 ¦ Priority: Critical Description: Test encryption. Subtasks: - Test round-trip - Test padding Technical Details: Verify with decryption. Deliverables: - Test files

### Acceptance Criteria

- ✓ Messages encrypt correctly

- ✓ Headers included

- ✓ Padding applied

- ✓ State updates atomically

### Technical Notes

- New ratchet key on first send after receive

### Dependencies

- US-5.2

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| State corruption on failure | High | Transactional updates |

User Story US-5.4: Message Decryption As a recipient, I want to decrypt received messages so that I can read communications.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 24 |

### Tasks Breakdown

Task 1: Decrypt Message Hours: 4 ¦ Priority: Critical Description: Implement message decryption. Subtasks: - Parse header - Get/derive message key - Decrypt ciphertext Technical Details: Handle authentication failure. Deliverables: - Decrypt method

Task 2: DH Ratchet Advancement Hours: 4 ¦ Priority: Critical Description: Process ratchet key in header. Subtasks: - Check if new ratchet key - Perform DH ratchet step Technical Details: Advance if new key received. Deliverables: - Ratchet advancement

Task 3: Out-of-Order Handling Hours: 6 ¦ Priority: Critical Description: Handle messages arriving out of order. Subtasks: - Store skipped message keys - Try skipped keys first - Enforce MAX_SKIP limit Technical Details: MAX_SKIP = 1000 messages. Deliverables: - OOO handling

Task 4: Skipped Key Storage Hours: 4 ¦ Priority: High Description: Store keys for skipped messages. Subtasks: - Key by (ratchet_key, message_num) - Delete after use or expiration Technical Details: Expire after 7 days. Deliverables: - Key storage

Task 5: Key Cleanup Hours: 3 ¦ Priority: Medium Description: Delete old keys. Subtasks: - Delete used message keys - Prune old skipped keys Technical Details: Minimize stored key material. Deliverables: - Cleanup code

Task 6: Tests Hours: 5 ¦ Priority: Critical Description: Test decryption. Subtasks: - Test in-order - Test out-of-order - Test skipped key expiration Technical Details: Comprehensive scenarios. Deliverables: - Test files

### Acceptance Criteria

- ✓ Decryption works in/out of order

- ✓ Skipped keys stored correctly

- ✓ MAX_SKIP enforced

- ✓ Old keys cleaned

### Technical Notes

- Try skipped keys before ratchet advance

### Dependencies

- US-5.3

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Key leakage from skipped keys | Medium | Expiration and limits |

User Story US-5.5: Session Persistence As a user, I want to have sessions persist across restarts so that conversations continue seamlessly.

| Priority | Story Points | Hours |
| --- | --- | --- |
| High | 5 | 15 |

### Tasks Breakdown

Task 1: Serialization Format Hours: 4 ¦ Priority: High Description: Define session storage format. Subtasks: - Serialize all state - Include version for evolution Technical Details: Binary format with encryption. Deliverables: - Format specification

Task 2: Secure Storage Hours: 5 ¦ Priority: Critical Description: Store sessions securely. Subtasks: - Encrypt with device key - Atomic writes Technical Details: Use platform secure storage. Deliverables: - Storage implementation

Task 3: Session Recovery Hours: 4 ¦ Priority: High Description: Load and validate sessions. Subtasks: - Deserialize state - Validate integrity Technical Details: Handle corrupted sessions. Deliverables: - Recovery code

Task 4: Tests Hours: 4 ¦ Priority: High Description: Test persistence. Subtasks: - Test save/load cycle - Test corruption handling Technical Details: Verify encryption works. Deliverables: - Test files

### Acceptance Criteria

- ✓ Sessions serialize correctly

- ✓ Encryption protects at rest

- ✓ Recovery handles corruption

### Technical Notes

- Key storage separate from session storage

### Dependencies

- US-5.4

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Data loss on corruption | High | Backup previous state |

# Sprint 6: Backend Infrastructure (Weeks 11-12)

Sprint Goal Build server infrastructure with REST API, SignalR hub, database, and user management.

## Sprint Objectives

- Create database schema with EF Core

- Implement user management API

- Build pre-key distribution endpoints

- Create SignalR message hub

- Implement message storage

## Sprint Metrics

| Metric | Value |
| --- | --- |
| Story Points | 34 |
| Hours | 102 |
| Risk | Medium |
| User Stories | 5 |

## User Stories

User Story US-6.1: Database Schema As a system, I want to have a database schema for data persistence so that user data and messages can be stored.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 22 |

### Tasks Breakdown

Task 1: Design Entity Model Hours: 4 ¦ Priority: Critical Description: Design database entities. Subtasks: - User entity - PreKeyBundle entities - Message entity - Device entity Technical Details: EF Core with PostgreSQL. Deliverables: - Entity classes

Task 2: Create User Entity Hours: 3 ¦ Priority: Critical Description: Define user table. Subtasks: - Id, Username, PasswordHash - Identity key reference - Registration timestamp Technical Details: Use GUID for Id. Deliverables: - User.cs

Task 3: Create PreKey Entities Hours: 4 ¦ Priority: Critical Description: Define pre-key tables. Subtasks: - IdentityKey table - SignedPreKey table - OneTimePreKey table Technical Details: Foreign key to User. Deliverables: - PreKey entities

Task 4: Create Message Entity Hours: 3 ¦ Priority: Critical Description: Define message storage. Subtasks: - Encrypted content - Sender/recipient - Timestamps Technical Details: Only encrypted blobs. Deliverables: - Message.cs

Task 5: Setup Migrations Hours: 3 ¦ Priority: High Description: Configure EF Core migrations. Subtasks: - Initial migration - Apply to database Technical Details: Use code-first migrations. Deliverables: - Migration files

Task 6: Create Indexes Hours: 2 ¦ Priority: Medium Description: Add database indexes. Subtasks: - Index on username - Index on recipient for messages Technical Details: Optimize queries. Deliverables: - Index configuration

Task 7: Integration Tests Hours: 4 ¦ Priority: High Description: Test database operations. Subtasks: - Test CRUD operations - Test relationships Technical Details: Use test container. Deliverables: - Test files

### Acceptance Criteria

- ✓ Schema supports all features

- ✓ Migrations run cleanly

- ✓ Queries performant

### Technical Notes

- Server never sees plaintext

### Dependencies

- US-1.4

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Schema changes difficult later | Medium | Design carefully upfront |

User Story US-6.2: User Management API As a user, I want to register and authenticate so that I can access the messaging service.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 23 |

### Tasks Breakdown

Task 1: Registration Endpoint Hours: 4 ¦ Priority: Critical Description: Implement user registration. Subtasks: - POST /api/users/register - Validate input - Hash password - Store user Technical Details: Use Argon2id for password. Deliverables: - Register endpoint

Task 2: Authentication Hours: 5 ¦ Priority: Critical Description: Implement JWT authentication. Subtasks: - POST /api/auth/login - Validate credentials - Generate JWT Technical Details: RS256 signing. Deliverables: - Login endpoint - JWT config

Task 3: Token Refresh Hours: 4 ¦ Priority: High Description: Implement refresh tokens. Subtasks: - POST /api/auth/refresh - Validate refresh token - Issue new tokens Technical Details: Refresh token rotation. Deliverables: - Refresh endpoint

Task 4: Profile Endpoints Hours: 3 ¦ Priority: Medium Description: User profile management. Subtasks: - GET /api/users/me - PUT /api/users/me Technical Details: Authenticated routes. Deliverables: - Profile endpoints

Task 5: Rate Limiting Hours: 3 ¦ Priority: Medium Description: Prevent abuse. Subtasks: - Limit login attempts - Limit registration Technical Details: Use sliding window. Deliverables: - Rate limiting middleware

Task 6: Tests Hours: 4 ¦ Priority: High Description: Test all endpoints. Subtasks: - Test success/failure paths - Test rate limiting Technical Details: Integration tests. Deliverables: - Test files

### Acceptance Criteria

- ✓ Users can register

- ✓ Authentication works

- ✓ Refresh tokens work

- ✓ Rate limiting active

### Technical Notes

- Never store plaintext passwords

### Dependencies

- US-6.1

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Auth bypass | Critical | Security testing |

User Story US-6.3: Pre-Key Distribution As a user, I want to upload and retrieve pre-key bundles so that key exchange can occur.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 6 | 20 |

### Tasks Breakdown

Task 1: Upload Endpoint Hours: 4 ¦ Priority: Critical Description: Upload pre-key bundle. Subtasks: - POST /api/keys/bundle - Validate bundle - Store keys Technical Details: Authenticated. Deliverables: - Upload endpoint

Task 2: Retrieval Endpoint Hours: 4 ¦ Priority: Critical Description: Get recipient's bundle. Subtasks: - GET /api/keys/bundle/{userId} - Return identity + signed + one OTP Technical Details: Consume one-time key. Deliverables: - Retrieval endpoint

Task 3: One-Time Key Consumption Hours: 4 ¦ Priority: Critical Description: Mark keys as used. Subtasks: - Delete after retrieval - Handle concurrent access Technical Details: Atomic operation. Deliverables: - Consumption logic

Task 4: Replenishment Notification Hours: 3 ¦ Priority: Medium Description: Notify when keys low. Subtasks: - Check count on retrieval - Notify via SignalR Technical Details: When <20 remaining. Deliverables: - Notification logic

Task 5: Bundle Validation Hours: 3 ¦ Priority: High Description: Validate uploaded bundles. Subtasks: - Check signatures - Validate formats Technical Details: Reject invalid bundles. Deliverables: - Validation code

Task 6: Tests Hours: 4 ¦ Priority: Critical Description: Test key distribution. Subtasks: - Test upload/retrieve - Test consumption Technical Details: Integration tests. Deliverables: - Test files

### Acceptance Criteria

- ✓ Bundles upload/retrieve correctly

- ✓ One-time keys consumed

- ✓ Invalid bundles rejected

### Technical Notes

- Server cannot read keys

### Dependencies

- US-6.2

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Key exhaustion | Medium | Replenishment notifications |

User Story US-6.4: SignalR Message Hub As a user, I want to receive messages in real-time so that I get messages instantly.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 22 |

### Tasks Breakdown

Task 1: Create SignalR Hub Hours: 4 ¦ Priority: Critical Description: Implement message hub. Subtasks: - Create ChatHub class - Add SendMessage method - Add authentication Technical Details: Authenticated connections. Deliverables: - ChatHub.cs

Task 2: Connection Management Hours: 4 ¦ Priority: Critical Description: Track connected users. Subtasks: - Map userId to connectionId - Handle reconnection Technical Details: Support multiple devices. Deliverables: - Connection manager

Task 3: Message Routing Hours: 4 ¦ Priority: Critical Description: Route messages to recipients. Subtasks: - Look up recipient connections - Send to all devices Technical Details: Fanout to devices. Deliverables: - Routing logic

Task 4: Presence Tracking Hours: 3 ¦ Priority: Medium Description: Track online status. Subtasks: - Update on connect/disconnect - Expose to clients Technical Details: Privacy-respecting. Deliverables: - Presence tracking

Task 5: Offline Queuing Hours: 5 ¦ Priority: Critical Description: Queue for offline users. Subtasks: - Store if no connection - Deliver on connect Technical Details: Persist to database. Deliverables: - Queuing logic

Task 6: Tests Hours: 4 ¦ Priority: High Description: Test hub functionality. Subtasks: - Test real-time delivery - Test offline queue Technical Details: SignalR test client. Deliverables: - Test files

### Acceptance Criteria

- ✓ Messages deliver <100ms when online

- ✓ Queue when offline

- ✓ Multi-device support

### Technical Notes

- SignalR handles reconnection

### Dependencies

- US-6.2

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Scaling limits | Medium | Redis backplane for scale |

User Story US-6.5: Message Storage As a user, I want to have messages stored for offline delivery so that I don't miss messages when disconnected.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 5 | 15 |

### Tasks Breakdown

Task 1: Encrypted Storage Hours: 4 ¦ Priority: Critical Description: Store encrypted messages. Subtasks: - Save ciphertext blob - Store metadata Technical Details: No plaintext access. Deliverables: - Storage methods

Task 2: Retrieval Endpoint Hours: 3 ¦ Priority: Critical Description: Retrieve pending messages. Subtasks: - GET /api/messages - Return undelivered Technical Details: Authenticated, paginated. Deliverables: - Retrieval endpoint

Task 3: Delivery Confirmation Hours: 3 ¦ Priority: Critical Description: Delete after delivery. Subtasks: - Client confirms receipt - Delete from storage Technical Details: Exactly-once delivery. Deliverables: - Confirmation endpoint

Task 4: Message Expiration Hours: 3 ¦ Priority: Medium Description: Expire old messages. Subtasks: - Configure TTL - Background cleanup Technical Details: Default: 30 days. Deliverables: - Expiration job

Task 5: Tests Hours: 4 ¦ Priority: High Description: Test storage. Subtasks: - Test store/retrieve/delete - Test expiration Technical Details: Integration tests. Deliverables: - Test files

### Acceptance Criteria

- ✓ Messages persist

- ✓ Deliver on reconnect

- ✓ Delete after delivery

- ✓ Expire old messages

### Technical Notes

- Server only sees encrypted blobs

### Dependencies

- US-6.4

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Storage growth | Medium | Expiration and quotas |

# Sprint 7: Web Client Application (Weeks 13-14)

Sprint Goal Build Blazor WebAssembly client with complete UI for secure messaging.

## Sprint Objectives

- Implement authentication UI

- Create conversation list

- Build message view

- Create message composition

- Implement contact management

- Add real-time updates

## Sprint Metrics

| Metric | Value |
| --- | --- |
| Story Points | 34 |
| Hours | 108 |
| Risk | Medium |
| User Stories | 6 |

## User Stories

User Story US-7.1: Authentication UI As a user, I want to login and register through the UI so that I can access the application.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 5 | 16 |

### Tasks Breakdown

Task 1: Login Page Hours: 4 ¦ Priority: Critical Description: Create login form. Subtasks: - Username/password fields - Submit button - Error display Technical Details: Blazor component. Deliverables: - Login.razor

Task 2: Registration Page Hours: 4 ¦ Priority: Critical Description: Create registration form. Subtasks: - Form fields - Validation - Submit logic Technical Details: Client-side validation. Deliverables: - Register.razor

Task 3: Auth State Management Hours: 4 ¦ Priority: Critical Description: Manage auth state. Subtasks: - Store tokens - Auto-refresh - Logout Technical Details: AuthenticationStateProvider. Deliverables: - Auth service

Task 4: Secure Token Storage Hours: 4 ¦ Priority: Critical Description: Store tokens securely. Subtasks: - Use localStorage carefully - Clear on logout Technical Details: Consider memory-only option. Deliverables: - Token storage

### Acceptance Criteria

- ✓ Login/register works

- ✓ Tokens stored securely

- ✓ Responsive design

### Technical Notes

- Consider IndexedDB for secure storage

### Dependencies

- US-6.2

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Token theft | High | Short expiry, refresh tokens |

User Story US-7.2: Conversation List As a user, I want to see my conversations so that I can select one to view.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 5 | 16 |

### Tasks Breakdown

Task 1: List Component Hours: 4 ¦ Priority: Critical Description: Create conversation list. Subtasks: - Load conversations - Display preview Technical Details: Virtualized list. Deliverables: - ConversationList.razor

Task 2: Item Component Hours: 3 ¦ Priority: High Description: Single conversation item. Subtasks: - Avatar - Name - Preview - Timestamp Technical Details: Reusable component. Deliverables: - ConversationItem.razor

Task 3: Unread Indicators Hours: 3 ¦ Priority: High Description: Show unread count. Subtasks: - Track read state - Display badge Technical Details: Update in real-time. Deliverables: - Unread logic

Task 4: Search/Filter Hours: 3 ¦ Priority: Medium Description: Search conversations. Subtasks: - Text search - Filter unread Technical Details: Client-side filtering. Deliverables: - Search component

Task 5: Tests Hours: 3 ¦ Priority: High Description: Test list component. Subtasks: - bUnit tests Technical Details: Component testing. Deliverables: - Test files

### Acceptance Criteria

- ✓ Conversations display

- ✓ Unread counts shown

- ✓ Search works

### Technical Notes

- Lazy load old conversations

### Dependencies

- US-6.4

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Performance with many conversations | Low | Virtualization |

User Story US-7.3: Message View As a user, I want to view conversation messages so that I can read chat history.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 5 | 18 |

### Tasks Breakdown

Task 1: Message List Hours: 4 ¦ Priority: Critical Description: Display messages. Subtasks: - Load messages - Scroll to bottom - Infinite scroll Technical Details: Virtualized list. Deliverables: - MessageList.razor

Task 2: Message Bubble Hours: 3 ¦ Priority: Critical Description: Single message display. Subtasks: - Sent/received styles - Timestamp - Status Technical Details: Different alignment. Deliverables: - MessageBubble.razor

Task 3: Status Indicators Hours: 3 ¦ Priority: Medium Description: Show message status. Subtasks: - Sending/sent/delivered/read Technical Details: Update from server. Deliverables: - Status logic

Task 4: Infinite Scroll Hours: 4 ¦ Priority: Medium Description: Load older messages. Subtasks: - Detect scroll to top - Load more Technical Details: Pagination. Deliverables: - Scroll loading

Task 5: Tests Hours: 4 ¦ Priority: High Description: Test message view. Subtasks: - Test rendering - Test scrolling Technical Details: bUnit tests. Deliverables: - Test files

### Acceptance Criteria

- ✓ Messages display correctly

- ✓ Timestamps shown

- ✓ Infinite scroll works

### Technical Notes

- Decrypt messages on client

### Dependencies

- US-7.2

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Memory with long conversations | Medium | Windowed virtualization |

User Story US-7.4: Message Composition As a user, I want to compose and send messages so that I can communicate with others.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 5 | 18 |

### Tasks Breakdown

Task 1: Input Component Hours: 3 ¦ Priority: Critical Description: Create message input. Subtasks: - Text area - Auto-resize Technical Details: Blazor input. Deliverables: - MessageInput.razor

Task 2: Send Logic Hours: 4 ¦ Priority: Critical Description: Encrypt and send. Subtasks: - Get session - Encrypt message - Send via SignalR Technical Details: Async operation. Deliverables: - Send logic

Task 3: Crypto Integration Hours: 5 ¦ Priority: Critical Description: Connect to crypto layer. Subtasks: - Access session - Call encrypt - Handle errors Technical Details: WASM crypto. Deliverables: - Crypto service

Task 4: Send Failure Handling Hours: 3 ¦ Priority: High Description: Handle send failures. Subtasks: - Retry logic - Error display Technical Details: Queue failed messages. Deliverables: - Error handling

Task 5: Tests Hours: 3 ¦ Priority: High Description: Test composition. Subtasks: - Test encrypt/send Technical Details: Integration tests. Deliverables: - Test files

### Acceptance Criteria

- ✓ Messages send encrypted

- ✓ UI responsive during send

- ✓ Errors handled

### Technical Notes

- Encrypt entirely on client

### Dependencies

- US-7.3

- US-5.3

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Crypto performance in WASM | Medium | Web Workers |

User Story US-7.5: Contact Management As a user, I want to manage contacts so that I can start new conversations.

| Priority | Story Points | Hours |
| --- | --- | --- |
| High | 8 | 22 |

### Tasks Breakdown

Task 1: Contact List Hours: 3 ¦ Priority: High Description: Display contacts. Subtasks: - Load contacts - Display names Technical Details: Sorted list. Deliverables: - ContactList.razor

Task 2: Contact Search Hours: 3 ¦ Priority: High Description: Search for users. Subtasks: - Search API - Display results Technical Details: Debounced search. Deliverables: - Search component

Task 3: New Conversation Flow Hours: 4 ¦ Priority: Critical Description: Start new conversation. Subtasks: - Select contact - Fetch pre-keys - Perform X3DH - Create session Technical Details: Full protocol flow. Deliverables: - New conversation logic

Task 4: Safety Number Verification Hours: 4 ¦ Priority: Critical Description: Verify contact identity. Subtasks: - Display fingerprint - Compare out-of-band Technical Details: Hybrid key fingerprint. Deliverables: - Verification UI

Task 5: Tests Hours: 4 ¦ Priority: High Description: Test contact management. Subtasks: - Test search - Test new conversation Technical Details: Integration tests. Deliverables: - Test files

### Acceptance Criteria

- ✓ Contacts display

- ✓ Search works

- ✓ New conversations created

- ✓ Safety numbers verifiable

### Technical Notes

- X3DH on first message

### Dependencies

- US-6.3

- US-4.2

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Failed key exchange | High | Clear error handling |

User Story US-7.6: Real-Time Updates As a user, I want to see messages instantly so that messaging feels real-time.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 6 | 18 |

### Tasks Breakdown

Task 1: SignalR Client Hours: 4 ¦ Priority: Critical Description: Connect to hub. Subtasks: - Create connection - Handle messages Technical Details: Blazor SignalR client. Deliverables: - SignalR service

Task 2: Connection Management Hours: 3 ¦ Priority: Critical Description: Handle reconnection. Subtasks: - Auto-reconnect - Queue during disconnect Technical Details: Exponential backoff. Deliverables: - Connection manager

Task 3: Message Handlers Hours: 4 ¦ Priority: Critical Description: Process received messages. Subtasks: - Decrypt - Update UI Technical Details: Reactive updates. Deliverables: - Message handlers

Task 4: Presence Updates Hours: 2 ¦ Priority: Low Description: Show online status. Subtasks: - Subscribe to presence - Update UI Technical Details: Privacy option. Deliverables: - Presence UI

Task 5: Tests Hours: 3 ¦ Priority: High Description: Test real-time. Subtasks: - Test message receipt - Test reconnection Technical Details: Integration tests. Deliverables: - Test files

### Acceptance Criteria

- ✓ Messages appear instantly

- ✓ Reconnects automatically

- ✓ Presence shows

### Technical Notes

- Decrypt on receive

### Dependencies

- US-6.4

- US-5.4

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Connection instability | Medium | Robust reconnection |

# Sprint 8: Integration & Polish (Weeks 15-16)

Sprint Goal Complete E2E testing, security review preparation, optimization, and documentation.

## Sprint Objectives

- Write comprehensive E2E tests

- Prepare security audit documentation

- Optimize performance

- Create user documentation

- Complete developer documentation

- Finalize academic paper

## Sprint Metrics

| Metric | Value |
| --- | --- |
| Story Points | 34 |
| Hours | 112 |
| Risk | Medium |
| User Stories | 6 |

## User Stories

User Story US-8.1: End-to-End Testing As a developer, I want to have comprehensive E2E tests so that system works correctly as a whole.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 8 | 25 |

### Tasks Breakdown

Task 1: Setup Playwright Hours: 3 ¦ Priority: High Description: Configure E2E framework. Subtasks: - Install Playwright - Configure for Blazor Technical Details: Playwright for .NET. Deliverables: - Playwright config

Task 2: Registration E2E Hours: 3 ¦ Priority: Critical Description: Test user registration. Subtasks: - Fill form - Submit - Verify account Technical Details: Full browser test. Deliverables: - Registration tests

Task 3: Key Exchange E2E Hours: 4 ¦ Priority: Critical Description: Test X3DH flow. Subtasks: - User A registers - User B registers - A initiates with B - Verify shared secret Technical Details: Two browser contexts. Deliverables: - Key exchange tests

Task 4: Messaging E2E Hours: 4 ¦ Priority: Critical Description: Test message send/receive. Subtasks: - Send message - Verify receipt - Verify decryption Technical Details: Full protocol flow. Deliverables: - Messaging tests

Task 5: Multi-Device E2E Hours: 4 ¦ Priority: Medium Description: Test multiple devices. Subtasks: - Login on two devices - Sync messages Technical Details: Multiple sessions. Deliverables: - Multi-device tests

Task 6: Offline E2E Hours: 4 ¦ Priority: Medium Description: Test offline/reconnect. Subtasks: - Disconnect - Send message - Reconnect - Verify delivery Technical Details: Network simulation. Deliverables: - Offline tests

Task 7: CI Integration Hours: 3 ¦ Priority: High Description: Run E2E in CI. Subtasks: - Configure pipeline - Handle artifacts Technical Details: GitHub Actions. Deliverables: - CI workflow

### Acceptance Criteria

- ✓ All E2E tests pass

- ✓ CI runs on every PR

### Technical Notes

- Use headed mode for debugging

### Dependencies

- US-7.6

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Flaky tests | Medium | Stable selectors, retry logic |

User Story US-8.2: Security Audit Prep As a security reviewer, I want to have audit documentation so that security review can be conducted.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 5 | 24 |

### Tasks Breakdown

Task 1: Security Architecture Doc Hours: 6 ¦ Priority: Critical Description: Document security design. Subtasks: - System overview - Crypto details - Trust boundaries Technical Details: Comprehensive document. Deliverables: - SECURITY_ARCHITECTURE.md

Task 2: Threat Model Hours: 5 ¦ Priority: Critical Description: Document threats. Subtasks: - STRIDE analysis - Attack trees Technical Details: Standard methodology. Deliverables: - THREAT_MODEL.md

Task 3: Crypto Specification Hours: 6 ¦ Priority: Critical Description: Detail crypto implementation. Subtasks: - Protocol spec - Key management - Algorithms Technical Details: Formal specification. Deliverables: - CRYPTO_SPEC.md

Task 4: Security Test Cases Hours: 4 ¦ Priority: High Description: Define security tests. Subtasks: - Penetration test cases - Crypto test cases Technical Details: Testable requirements. Deliverables: - Security test doc

Task 5: Key Management Doc Hours: 3 ¦ Priority: High Description: Document key lifecycle. Subtasks: - Generation - Storage - Rotation - Deletion Technical Details: Best practices. Deliverables: - KEY_MANAGEMENT.md

### Acceptance Criteria

- ✓ Documentation complete

- ✓ Ready for external review

### Technical Notes

- Follow OWASP guidelines

### Dependencies

- US-5.5

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Incomplete documentation | Medium | Checklist review |

User Story US-8.3: Performance Optimization As a user, I want to have a fast application so that messaging feels instant.

| Priority | Story Points | Hours |
| --- | --- | --- |
| High | 5 | 20 |

### Tasks Breakdown

Task 1: Profile Crypto Hours: 4 ¦ Priority: High Description: Profile crypto operations. Subtasks: - Identify bottlenecks - Measure times Technical Details: Benchmark tools. Deliverables: - Profile report

Task 2: Optimize Key Exchange Hours: 5 ¦ Priority: High Description: Speed up X3DH. Subtasks: - Parallel operations - Cache where safe Technical Details: Async parallelism. Deliverables: - Optimized X3DH

Task 3: Optimize Encryption Hours: 4 ¦ Priority: High Description: Speed up message encryption. Subtasks: - Buffer management - Reduce allocations Technical Details: Memory optimization. Deliverables: - Optimized encryption

Task 4: WASM Optimization Hours: 3 ¦ Priority: Medium Description: Optimize WASM loading. Subtasks: - Lazy loading - AOT where beneficial Technical Details: Blazor optimization. Deliverables: - Faster load

Task 5: Performance Benchmarks Hours: 4 ¦ Priority: High Description: Create benchmark suite. Subtasks: - Benchmark all operations - Document baselines Technical Details: BenchmarkDotNet. Deliverables: - Benchmark suite

### Acceptance Criteria

- ✓ Key exchange <500ms

- ✓ Message encryption <50ms

- ✓ E2E latency <200ms

### Technical Notes

- Measure on representative hardware

### Dependencies

- US-5.5

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| WASM limitations | Medium | Web Workers for heavy crypto |

User Story US-8.4: User Documentation As a user, I want to have documentation so that I can use the app securely.

| Priority | Story Points | Hours |
| --- | --- | --- |
| High | 5 | 14 |

### Tasks Breakdown

Task 1: Getting Started Guide Hours: 3 ¦ Priority: High Description: Write user guide. Subtasks: - Installation - First message Technical Details: User-friendly language. Deliverables: - Getting started

Task 2: Safety Number Guide Hours: 3 ¦ Priority: Critical Description: Document verification. Subtasks: - Why important - How to verify Technical Details: Screenshots. Deliverables: - Verification guide

Task 3: FAQ Hours: 2 ¦ Priority: Medium Description: Answer common questions. Subtasks: - Compile questions - Write answers Technical Details: Searchable format. Deliverables: - FAQ document

Task 4: Privacy Policy Hours: 3 ¦ Priority: Critical Description: Define privacy practices. Subtasks: - Data collection - Data usage Technical Details: Legal review. Deliverables: - Privacy policy

Task 5: Terms of Service Hours: 3 ¦ Priority: Critical Description: Define usage terms. Subtasks: - Acceptable use - Limitations Technical Details: Legal review. Deliverables: - ToS document

### Acceptance Criteria

- ✓ All docs complete

- ✓ Legal docs reviewed

### Technical Notes

- Plain language

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Legal issues | Medium | Legal review |

User Story US-8.5: Developer Documentation As a developer, I want to have API documentation so that I can contribute to the project.

| Priority | Story Points | Hours |
| --- | --- | --- |
| High | 5 | 17 |

### Tasks Breakdown

Task 1: API Documentation Hours: 3 ¦ Priority: High Description: Document REST API. Subtasks: - Generate Swagger - Add examples Technical Details: OpenAPI spec. Deliverables: - API docs

Task 2: Architecture Overview Hours: 4 ¦ Priority: High Description: Document architecture. Subtasks: - System diagram - Component overview Technical Details: Diagrams + text. Deliverables: - Architecture doc

Task 3: Crypto Library API Hours: 4 ¦ Priority: High Description: Document crypto API. Subtasks: - All public APIs - Usage examples Technical Details: XML doc comments. Deliverables: - Crypto API docs

Task 4: Contribution Guide Hours: 3 ¦ Priority: High Description: Detailed contributor guide. Subtasks: - Setup - Workflow - Standards Technical Details: Step-by-step. Deliverables: - Updated CONTRIBUTING.md

Task 5: Deployment Guide Hours: 3 ¦ Priority: High Description: Document deployment. Subtasks: - Docker deployment - Cloud options Technical Details: Infrastructure as code. Deliverables: - Deployment guide

### Acceptance Criteria

- ✓ Docs complete

- ✓ New dev can onboard

### Technical Notes

- Keep updated

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Docs out of date | Low | Doc generation |

User Story US-8.6: Academic Paper As a researcher, I want to finalize the academic paper so that it can be submitted for publication.

| Priority | Story Points | Hours |
| --- | --- | --- |
| Critical | 6 | 22 |

### Tasks Breakdown

Task 1: Performance Evaluation Hours: 6 ¦ Priority: Critical Description: Complete eval section. Subtasks: - Run benchmarks - Create tables/graphs - Write analysis Technical Details: LaTeX tables. Deliverables: - Evaluation section

Task 2: Security Analysis Hours: 6 ¦ Priority: Critical Description: Finalize security section. Subtasks: - Formal arguments - Comparison Technical Details: Rigorous analysis. Deliverables: - Security section

Task 3: Related Work Hours: 4 ¦ Priority: High Description: Complete literature review. Subtasks: - Add recent papers - Compare approaches Technical Details: Academic writing. Deliverables: - Related work section

Task 4: References Hours: 2 ¦ Priority: High Description: Complete bibliography. Subtasks: - Format all refs - Verify citations Technical Details: BibTeX. Deliverables: - References

Task 5: Formatting Hours: 2 ¦ Priority: High Description: Format for venue. Subtasks: - Apply template - Check length Technical Details: Conference template. Deliverables: - Formatted paper

Task 6: Advisor Review Hours: 4 ¦ Priority: Critical Description: Get feedback and revise. Subtasks: - Submit draft - Address feedback Technical Details: Iteration. Deliverables: - Final paper

### Acceptance Criteria

- ✓ Paper complete

- ✓ Advisor approved

- ✓ Ready for submission

### Technical Notes

- Target venue selected

### Dependencies

- US-8.3

### Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Feedback delays | Medium | Early submission |