SECURECHAT

Phase 1 Sprint Planning

Web Foundation (16 Weeks)

Version 1.0 | January 2025

# Phase 1 Overview

## Objectives

Phase 1 delivers the foundational web-based secure messaging application with the complete hybrid post-quantum cryptographic implementation.

- Implement Hybrid Post-Quantum X3DH key exchange

- Implement Hybrid Double Ratchet algorithm

- Build Blazor WebAssembly client application

- Build ASP.NET Core backend with SignalR

- Complete academic research paper

- Achieve security audit readiness

## Timeline Summary

| Sprint | Duration | Focus Area | Key Deliverable |
| --- | --- | --- | --- |
| Sprint 1 | Weeks 1-2 | Foundation & Setup | Project scaffolding, CI/CD |
| Sprint 2 | Weeks 3-4 | Classical Crypto | X25519, Ed25519, AES-GCM |
| Sprint 3 | Weeks 5-6 | Post-Quantum Crypto | Kyber, Dilithium integration |
| Sprint 4 | Weeks 7-8 | Hybrid X3DH | Complete key exchange protocol |
| Sprint 5 | Weeks 9-10 | Double Ratchet | Message encryption protocol |
| Sprint 6 | Weeks 11-12 | Backend & API | Server infrastructure |
| Sprint 7 | Weeks 13-14 | Web Client | Blazor WASM application |
| Sprint 8 | Weeks 15-16 | Integration & Polish | E2E testing, documentation |

# Sprint 1: Foundation & Setup (Weeks 1-2)

## Sprint Goal

Establish project infrastructure, development environment, and core architecture patterns that will support all subsequent development.

## User Stories

### US-1.1: Project Repository Setup

As a developer, I want a well-organized repository structure so that I can navigate and contribute to the codebase efficiently.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Create GitHub repository with branch protection | 2 | High |
| Set up solution structure (src/, tests/, docs/) | 3 | High |
| Configure .editorconfig and code style rules | 2 | Medium |
| Create README.md with project overview | 2 | Medium |
| Set up CONTRIBUTING.md and CODE_OF_CONDUCT.md | 2 | Low |

Acceptance Criteria: Repository is public, has proper structure, branch protection enabled, and documentation in place.

### US-1.2: CI/CD Pipeline

As a developer, I want automated build and test pipelines so that code quality is maintained automatically.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Set up GitHub Actions workflow for .NET build | 4 | High |
| Configure automated testing on PR | 4 | High |
| Add code coverage reporting (Codecov) | 3 | Medium |
| Configure security scanning (CodeQL) | 3 | Medium |
| Set up artifact publishing | 2 | Low |

Acceptance Criteria: All PRs trigger build, test, and security scan. Coverage reports generated automatically.

### US-1.3: Development Environment

As a developer, I want containerized development environment so that setup is consistent across machines.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Create Docker Compose for local development | 4 | High |
| Configure PostgreSQL container | 2 | High |
| Create development certificates for HTTPS | 2 | Medium |
| Document setup process | 2 | Medium |

Acceptance Criteria: New developer can run 'docker-compose up' and have full environment within 5 minutes.

### US-1.4: Core Project Structure

As a architect, I want Clean Architecture project organization so that the codebase is maintainable and testable.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Create SecureChat.Core class library | 3 | High |
| Create SecureChat.Crypto class library | 3 | High |
| Create SecureChat.Infrastructure class library | 3 | High |
| Create SecureChat.Api web project | 3 | High |
| Create SecureChat.Web.Client Blazor WASM project | 3 | High |
| Create test projects for each library | 4 | High |
| Configure project references and dependencies | 2 | Medium |

Acceptance Criteria: Solution builds successfully, all projects reference correctly, dependency flow follows Clean Architecture.

## Sprint 1 Summary

| Metric | Value |
| --- | --- |
| Total Story Points | 21 |
| Total Estimated Hours | 53 |
| Risk Level | Low |
| Dependencies | None |

# Sprint 2: Classical Cryptography (Weeks 3-4)

## Sprint Goal

Implement all classical cryptographic primitives required for the Signal Protocol foundation, with comprehensive testing and documentation.

## User Stories

### US-2.1: Key Pair Generation

As a system, I need to generate secure key pairs so that users can establish encrypted communications.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Implement Ed25519 key pair generation | 4 | High |
| Implement X25519 key pair generation | 4 | High |
| Create IKeyPair interface and abstractions | 3 | High |
| Implement secure key serialization | 4 | High |
| Add key validation methods | 3 | Medium |
| Write unit tests (min 90% coverage) | 6 | High |
| Document key formats and usage | 2 | Medium |

Acceptance Criteria: Keys generate in <10ms, pass NIST test vectors, secure memory handling verified.

### US-2.2: Digital Signatures

As a system, I need to create and verify digital signatures so that message authenticity can be verified.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Implement Ed25519 signing | 4 | High |
| Implement Ed25519 verification | 4 | High |
| Create IDigitalSignature interface | 2 | High |
| Implement signature serialization | 2 | Medium |
| Write unit tests with NIST vectors | 4 | High |
| Benchmark signing performance | 2 | Medium |

Acceptance Criteria: Signatures pass all NIST test vectors, sign <5ms, verify <5ms.

### US-2.3: Diffie-Hellman Key Exchange

As a system, I need to perform X25519 key exchange so that shared secrets can be established.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Implement X25519 DH function | 4 | High |
| Create shared secret derivation | 3 | High |
| Implement constant-time comparison | 3 | High |
| Add DH result validation | 2 | Medium |
| Write unit tests with RFC 7748 vectors | 4 | High |
| Document security considerations | 2 | Medium |

Acceptance Criteria: DH passes RFC 7748 test vectors, constant-time verified, <2ms per exchange.

### US-2.4: Symmetric Encryption

As a system, I need AES-256-GCM encryption so that messages can be securely encrypted.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Implement AES-256-GCM encryption | 4 | High |
| Implement AES-256-GCM decryption | 4 | High |
| Create secure nonce generation | 3 | High |
| Implement authenticated data support | 3 | Medium |
| Add message size validation | 2 | Medium |
| Write unit tests with NIST vectors | 4 | High |
| Benchmark encryption throughput | 2 | Low |

Acceptance Criteria: Encryption passes NIST GCM test vectors, throughput >100MB/s, nonce uniqueness guaranteed.

### US-2.5: Key Derivation

As a system, I need HKDF key derivation so that cryptographic keys can be derived from shared secrets.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Implement HKDF-SHA256 extract | 3 | High |
| Implement HKDF-SHA256 expand | 3 | High |
| Create convenience method for extract-expand | 2 | Medium |
| Add info parameter support | 2 | Medium |
| Write unit tests with RFC 5869 vectors | 3 | High |
| Document KDF usage patterns | 2 | Medium |

Acceptance Criteria: HKDF passes RFC 5869 test vectors, secure memory handling.

## Sprint 2 Summary

| Metric | Value |
| --- | --- |
| Total Story Points | 34 |
| Total Estimated Hours | 89 |
| Risk Level | Medium |
| Dependencies | Sprint 1 completion |

# Sprint 3: Post-Quantum Cryptography (Weeks 5-6)

## Sprint Goal

Integrate CRYSTALS-Kyber and CRYSTALS-Dilithium post-quantum algorithms, establishing the foundation for hybrid cryptography.

## User Stories

### US-3.1: Kyber Key Encapsulation

As a system, I need Kyber-768 KEM so that quantum-resistant key exchange can be performed.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Integrate BouncyCastle Kyber implementation | 4 | High |
| Create IKeyEncapsulation interface | 3 | High |
| Implement Kyber-768 key generation | 4 | High |
| Implement encapsulation function | 4 | High |
| Implement decapsulation function | 4 | High |
| Add key serialization/deserialization | 3 | Medium |
| Write unit tests with KAT vectors | 6 | High |
| Benchmark performance | 2 | Medium |

Acceptance Criteria: Kyber passes all KAT vectors, keygen <50ms, encaps <20ms, decaps <20ms.

### US-3.2: Dilithium Digital Signatures

As a system, I need Dilithium-3 signatures so that quantum-resistant authentication is available.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Integrate BouncyCastle Dilithium | 4 | High |
| Implement Dilithium-3 key generation | 4 | High |
| Implement signing function | 4 | High |
| Implement verification function | 4 | High |
| Add signature serialization | 2 | Medium |
| Write unit tests with KAT vectors | 5 | High |
| Benchmark and compare to Ed25519 | 2 | Medium |

Acceptance Criteria: Dilithium passes all KAT vectors, sign <30ms, verify <15ms.

### US-3.3: Hybrid Key Pair

As a system, I need combined classical/PQ key pairs so that both security guarantees can be achieved.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Design HybridKeyPair data structure | 3 | High |
| Implement hybrid identity key (Ed25519 + Dilithium) | 4 | High |
| Implement hybrid exchange key (X25519 + Kyber) | 4 | High |
| Create serialization format | 4 | Medium |
| Implement key fingerprinting | 3 | Medium |
| Write comprehensive unit tests | 4 | High |
| Document hybrid key format | 2 | Medium |

Acceptance Criteria: Hybrid keys generate correctly, serialize/deserialize without loss, fingerprints unique.

### US-3.4: Hybrid Shared Secret

As a system, I need combined shared secret derivation so that hybrid key exchange produces secure keys.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Design shared secret combination strategy | 4 | High |
| Implement X25519 + Kyber secret combination | 6 | High |
| Create hybrid KDF wrapper | 4 | High |
| Add domain separation for different contexts | 3 | Medium |
| Write security analysis documentation | 4 | High |
| Comprehensive testing | 4 | High |

Acceptance Criteria: Shared secrets combine correctly, security analysis documented, tests pass.

## Sprint 3 Summary

| Metric | Value |
| --- | --- |
| Total Story Points | 34 |
| Total Estimated Hours | 96 |
| Risk Level | High |
| Dependencies | Sprint 2 completion, BouncyCastle library |

# Sprint 4: Hybrid X3DH Protocol (Weeks 7-8)

## Sprint Goal

Implement the complete Hybrid Post-Quantum X3DH key agreement protocol, enabling secure initial key exchange between users.

## User Stories

### US-4.1: Pre-Key Bundle Generation

As a user, I need to generate and publish pre-key bundles so that others can initiate secure conversations with me.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Design PreKeyBundle data structure | 3 | High |
| Implement identity key inclusion | 2 | High |
| Implement signed pre-key generation | 4 | High |
| Implement one-time pre-key batch generation | 4 | High |
| Create pre-key signing with hybrid signature | 4 | High |
| Implement bundle serialization | 3 | Medium |
| Add bundle validation | 3 | Medium |
| Write unit tests | 4 | High |

Acceptance Criteria: Bundles generate correctly, signatures verify, serialization round-trips.

### US-4.2: X3DH Initiator

As a sender, I need to perform X3DH as initiator so that I can establish a shared secret with a recipient.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Implement DH calculations (DH1-DH4) | 6 | High |
| Add Kyber encapsulation for each DH | 6 | High |
| Implement shared secret combination | 4 | High |
| Create initial message structure | 3 | High |
| Add associated data construction | 3 | Medium |
| Implement one-time pre-key consumption | 3 | Medium |
| Write unit tests | 5 | High |
| Document protocol flow | 3 | Medium |

Acceptance Criteria: Initiator produces valid initial message, shared secret matches responder.

### US-4.3: X3DH Responder

As a recipient, I need to process X3DH initial messages so that I can derive the shared secret.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Implement initial message parsing | 3 | High |
| Implement DH calculations (responder side) | 6 | High |
| Add Kyber decapsulation | 6 | High |
| Verify signature on initial message | 3 | High |
| Derive shared secret | 4 | High |
| Handle missing one-time pre-key case | 3 | Medium |
| Write unit tests | 5 | High |

Acceptance Criteria: Responder derives identical shared secret, handles all edge cases.

### US-4.4: Session Initialization

As a system, I need to initialize Double Ratchet sessions so that ongoing encryption can begin.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Design Session data structure | 4 | High |
| Implement session state initialization | 4 | High |
| Create root key derivation | 3 | High |
| Initialize chain keys | 3 | High |
| Set up ratchet state | 4 | High |
| Write unit tests | 4 | High |
| Document session lifecycle | 2 | Medium |

Acceptance Criteria: Sessions initialize correctly from X3DH output, ready for Double Ratchet.

## Sprint 4 Summary

| Metric | Value |
| --- | --- |
| Total Story Points | 34 |
| Total Estimated Hours | 105 |
| Risk Level | High |
| Dependencies | Sprint 3 completion |

# Sprint 5: Double Ratchet Algorithm (Weeks 9-10)

## Sprint Goal

Implement the complete Hybrid Double Ratchet algorithm for ongoing message encryption with forward secrecy and post-compromise security.

## User Stories

### US-5.1: Symmetric Ratchet

As a system, I need symmetric key ratcheting so that each message has a unique encryption key.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Implement chain key derivation | 4 | High |
| Implement message key derivation | 4 | High |
| Create ChainState data structure | 3 | High |
| Add message counter management | 3 | Medium |
| Implement key deletion after use | 3 | High |
| Write unit tests | 4 | High |

Acceptance Criteria: Chain advances correctly, keys derived match specification, old keys deleted.

### US-5.2: DH Ratchet

As a system, I need hybrid DH ratcheting so that new shared secrets are established with each exchange.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Implement DH ratchet step (classical) | 5 | High |
| Add Kyber ratchet step (post-quantum) | 6 | High |
| Combine classical and PQ ratchet outputs | 4 | High |
| Update root key on ratchet | 3 | High |
| Generate new ratchet key pairs | 3 | High |
| Write unit tests | 5 | High |

Acceptance Criteria: Ratchet advances correctly, both parties derive same keys.

### US-5.3: Message Encryption

As a sender, I need to encrypt messages so that only the intended recipient can read them.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Implement message encryption wrapper | 4 | High |
| Add header construction | 3 | High |
| Implement header encryption (optional) | 4 | Medium |
| Add padding to hide message length | 3 | Medium |
| Create EncryptedMessage structure | 3 | High |
| Handle ratchet state updates | 4 | High |
| Write unit tests | 5 | High |

Acceptance Criteria: Messages encrypt correctly, headers included, padding applied.

### US-5.4: Message Decryption

As a recipient, I need to decrypt messages so that I can read received communications.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Implement message decryption | 4 | High |
| Handle header decryption | 3 | High |
| Process ratchet advancement | 4 | High |
| Implement out-of-order message handling | 6 | High |
| Add skipped message key storage | 4 | High |
| Implement message key cleanup | 3 | Medium |
| Write unit tests | 5 | High |

Acceptance Criteria: All messages decrypt correctly, out-of-order handled, old keys cleaned.

### US-5.5: Session Persistence

As a user, I need session state to persist so that conversations continue across app restarts.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Design session serialization format | 4 | High |
| Implement secure session storage | 5 | High |
| Add session recovery logic | 4 | High |
| Implement session backup/restore | 4 | Medium |
| Handle corrupted session recovery | 4 | Medium |
| Write unit tests | 4 | High |

Acceptance Criteria: Sessions serialize/deserialize correctly, encryption continues after reload.

## Sprint 5 Summary

| Metric | Value |
| --- | --- |
| Total Story Points | 34 |
| Total Estimated Hours | 117 |
| Risk Level | High |
| Dependencies | Sprint 4 completion |

# Sprint 6: Backend Infrastructure (Weeks 11-12)

## Sprint Goal

Build the server infrastructure including REST API, SignalR hub, database, and user management.

## User Stories

### US-6.1: Database Schema

As a system, I need a database schema so that user data and messages can be persisted.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Design entity relationship model | 4 | High |
| Create User entity and configuration | 3 | High |
| Create PreKeyBundle entities | 4 | High |
| Create Message entity (encrypted) | 3 | High |
| Create Device entity for multi-device | 3 | Medium |
| Set up EF Core migrations | 3 | High |
| Create database indexes | 2 | Medium |
| Write integration tests | 4 | High |

Acceptance Criteria: Schema supports all features, migrations run cleanly, queries performant.

### US-6.2: User Management API

As a user, I need to register and authenticate so that I can use the messaging service.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Implement user registration endpoint | 4 | High |
| Implement authentication (JWT) | 5 | High |
| Add refresh token support | 4 | High |
| Implement user profile endpoints | 3 | Medium |
| Add rate limiting | 3 | Medium |
| Write API tests | 4 | High |

Acceptance Criteria: Users can register, login, refresh tokens, rate limiting active.

### US-6.3: Pre-Key Distribution

As a user, I need to upload and retrieve pre-key bundles so that key exchange can occur.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Implement pre-key bundle upload endpoint | 4 | High |
| Implement pre-key bundle retrieval endpoint | 4 | High |
| Add one-time pre-key consumption logic | 4 | High |
| Implement pre-key replenishment notification | 3 | Medium |
| Add pre-key validation | 3 | Medium |
| Write API tests | 4 | High |

Acceptance Criteria: Pre-keys upload/retrieve correctly, one-time keys consumed properly.

### US-6.4: SignalR Message Hub

As a user, I need real-time message delivery so that I receive messages instantly.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Create SignalR hub | 4 | High |
| Implement connection management | 4 | High |
| Add message routing | 4 | High |
| Implement presence tracking | 3 | Medium |
| Add typing indicators | 2 | Low |
| Handle offline message queuing | 5 | High |
| Write integration tests | 4 | High |

Acceptance Criteria: Messages deliver in <100ms when online, queue when offline.

### US-6.5: Message Storage

As a user, I need messages stored for offline delivery so that I don't miss messages when disconnected.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Implement encrypted message storage | 4 | High |
| Add message retrieval endpoint | 3 | High |
| Implement message deletion after delivery | 3 | High |
| Add message expiration | 3 | Medium |
| Create delivery receipts | 4 | Medium |
| Write tests | 4 | High |

Acceptance Criteria: Messages persist encrypted, deliver on reconnect, delete after delivery.

## Sprint 6 Summary

| Metric | Value |
| --- | --- |
| Total Story Points | 34 |
| Total Estimated Hours | 110 |
| Risk Level | Medium |
| Dependencies | Sprint 5 completion |

# Sprint 7: Web Client Application (Weeks 13-14)

## Sprint Goal

Build the Blazor WebAssembly client application with complete UI for secure messaging.

## User Stories

### US-7.1: Authentication UI

As a user, I need login and registration screens so that I can access the application.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Create login page component | 4 | High |
| Create registration page component | 4 | High |
| Implement form validation | 3 | High |
| Add authentication state management | 4 | High |
| Implement secure token storage | 4 | High |
| Add password strength indicator | 2 | Low |
| Style with responsive design | 3 | Medium |

Acceptance Criteria: Users can register and login, tokens stored securely, responsive on mobile.

### US-7.2: Conversation List

As a user, I need to see my conversations so that I can select one to view.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Create conversation list component | 4 | High |
| Implement conversation item component | 3 | High |
| Add unread message indicators | 3 | Medium |
| Implement search/filter | 3 | Medium |
| Add conversation sorting | 2 | Medium |
| Implement pull-to-refresh | 2 | Low |
| Style with responsive design | 3 | Medium |

Acceptance Criteria: Conversations display with latest message preview, unread counts shown.

### US-7.3: Message View

As a user, I need to view conversation messages so that I can read the chat history.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Create message list component | 4 | High |
| Create message bubble component | 3 | High |
| Add timestamp display | 2 | Medium |
| Implement message status indicators | 3 | Medium |
| Add scroll-to-bottom behavior | 2 | Medium |
| Implement infinite scroll for history | 4 | Medium |
| Style message bubbles | 3 | Medium |

Acceptance Criteria: Messages display correctly, timestamps shown, status indicators work.

### US-7.4: Message Composition

As a user, I need to compose and send messages so that I can communicate with others.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Create message input component | 3 | High |
| Implement send button/enter key | 2 | High |
| Add emoji picker (basic) | 3 | Low |
| Implement typing indicator | 3 | Medium |
| Add message drafts | 2 | Low |
| Connect to crypto layer | 5 | High |
| Handle send failures | 3 | Medium |

Acceptance Criteria: Messages send and encrypt correctly, UI responsive during encryption.

### US-7.5: Contact Management

As a user, I need to manage contacts so that I can start new conversations.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Create contact list component | 3 | High |
| Implement contact search | 3 | High |
| Add contact request flow | 4 | High |
| Create new conversation flow | 4 | High |
| Add contact verification (safety number) | 4 | High |
| Style contact components | 2 | Medium |

Acceptance Criteria: Users can find contacts, start conversations, verify safety numbers.

### US-7.6: Real-time Updates

As a user, I need real-time message updates so that I see new messages instantly.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Implement SignalR client | 4 | High |
| Handle connection management | 3 | High |
| Add reconnection logic | 3 | High |
| Implement message handlers | 4 | High |
| Add presence updates | 2 | Medium |
| Handle typing indicators | 2 | Low |

Acceptance Criteria: Messages appear instantly, reconnects automatically, presence updates.

## Sprint 7 Summary

| Metric | Value |
| --- | --- |
| Total Story Points | 34 |
| Total Estimated Hours | 107 |
| Risk Level | Medium |
| Dependencies | Sprint 6 completion |

# Sprint 8: Integration & Polish (Weeks 15-16)

## Sprint Goal

Complete end-to-end integration testing, security review, performance optimization, and documentation for Phase 1 release.

## User Stories

### US-8.1: End-to-End Testing

As a developer, I need comprehensive E2E tests so that the system works correctly as a whole.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Set up Playwright test framework | 3 | High |
| Write user registration E2E test | 3 | High |
| Write key exchange E2E test | 4 | High |
| Write message send/receive E2E test | 4 | High |
| Write multi-device E2E test | 4 | Medium |
| Write offline/reconnect E2E test | 4 | Medium |
| Set up E2E test CI pipeline | 3 | High |

Acceptance Criteria: All E2E tests pass, CI runs tests on every PR.

### US-8.2: Security Audit Preparation

As a security reviewer, I need audit documentation so that the security review can be conducted.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Create security architecture document | 6 | High |
| Document threat model | 5 | High |
| Write cryptographic specification | 6 | High |
| Create security test cases | 4 | High |
| Document key management procedures | 4 | High |
| Prepare security questionnaire responses | 3 | Medium |

Acceptance Criteria: Documentation complete, ready for external security review.

### US-8.3: Performance Optimization

As a user, I need the application to be fast so that messaging feels instant.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Profile cryptographic operations | 4 | High |
| Optimize key exchange performance | 5 | High |
| Optimize message encryption | 4 | High |
| Add lazy loading for WASM | 3 | Medium |
| Optimize SignalR message handling | 3 | Medium |
| Create performance benchmarks | 4 | High |

Acceptance Criteria: Key exchange <500ms, message encryption <50ms, E2E latency <200ms.

### US-8.4: User Documentation

As a user, I need documentation so that I can understand how to use the application securely.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Write getting started guide | 3 | High |
| Document safety number verification | 3 | High |
| Create FAQ document | 2 | Medium |
| Write privacy policy | 3 | High |
| Create terms of service | 3 | High |
| Add in-app help | 2 | Medium |

Acceptance Criteria: Users can self-serve documentation, legal documents complete.

### US-8.5: Developer Documentation

As a developer, I need API documentation so that I can contribute to the project.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Generate API documentation (Swagger) | 3 | High |
| Write architecture overview | 4 | High |
| Document crypto library API | 4 | High |
| Create contribution guide | 3 | High |
| Write deployment guide | 4 | High |
| Set up documentation site | 3 | Medium |

Acceptance Criteria: New developers can onboard from docs, API fully documented.

### US-8.6: Academic Paper Finalization

As a researcher, I need to finalize the academic paper so that it can be submitted for publication.

| Task | Est. Hours | Priority |
| --- | --- | --- |
| Complete performance evaluation section | 6 | High |
| Finalize security analysis | 6 | High |
| Write related work section | 4 | High |
| Complete references | 2 | High |
| Format for target venue | 3 | High |
| Advisor review and revision | 4 | High |

Acceptance Criteria: Paper ready for submission, advisor approved.

## Sprint 8 Summary

| Metric | Value |
| --- | --- |
| Total Story Points | 34 |
| Total Estimated Hours | 120 |
| Risk Level | Medium |
| Dependencies | Sprint 7 completion |

# Phase 1 Summary

## Total Effort

| Sprint | Story Points | Hours | Focus |
| --- | --- | --- | --- |
| Sprint 1 | 21 | 53 | Foundation |
| Sprint 2 | 34 | 89 | Classical Crypto |
| Sprint 3 | 34 | 96 | Post-Quantum Crypto |
| Sprint 4 | 34 | 105 | Hybrid X3DH |
| Sprint 5 | 34 | 117 | Double Ratchet |
| Sprint 6 | 34 | 110 | Backend |
| Sprint 7 | 34 | 107 | Web Client |
| Sprint 8 | 34 | 120 | Integration |
| TOTAL | 259 | 797 | - |

## Key Milestones

| Milestone | Target Date | Sprint | Criteria |
| --- | --- | --- | --- |
| Development Environment Ready | Week 2 | 1 | CI/CD operational |
| Crypto Library Complete | Week 6 | 3 | All primitives tested |
| Protocol Complete | Week 10 | 5 | X3DH + Double Ratchet working |
| MVP Functional | Week 14 | 7 | End-to-end messaging works |
| Phase 1 Release | Week 16 | 8 | All acceptance criteria met |

## Success Criteria

- All user stories completed and accepted

- Code coverage > 80%

- All security tests passing

- Performance benchmarks met

- Documentation complete

- Academic paper submission-ready

- Ready for security audit